## Divsion Wise Lanuishing project
Languished projects sanctioned under JKIDFC by the High Power Committee as on 29-11-2018.
S.No | Name of Langusihed Project | Online Approved Cost Of Schemes | Approved Balance cost for completion (Rs in Lacs) |  |  |  |  | Approved Balance cost for completion (Rs in Lacs) |  |  |  | Weather alloted | Alloted Cost | Work Started (Yes/No) | Date of Start of Work |  |  |  |  | Expenditure booked up to 10-2018 | [5 empty] | Balance Cost as on date | [5 empty] | Proposed Allocation during 2018-19 under CSS +MSS |  | Total MSS+CSS | No. of Works tendered | Tendered Cost | No. of works Alloted | Alloted Cost | No. of works takes up for execution | Execution % | No. of works Completed as on date | Likely Completion date for ongoing works | Balnnce Cost for Completion of the Scheme during 2018-19 | Targeted Schemes during 2018-19 | Balnnce Cost for Completion of the Scheme during 2019-20&21 | Targeted Schemes during 2019-20 | Status of Water Supply Scheme | [5 empty] | Percentage of Over all Phy. Completion of the scheme | Targeted time line | Scheme Id | Remarks
[8 empty] | Civil | Mech. | GW | Total | [20 empty] | MSS | CSS | [13 empty] | Civil Components of the Scheme | Phy.Percentage (%) of completion of the Component | Mech. Components of the Scheme | Phy.Percentage (%) of completion of the Component | Ground Water Components of the Scheme | Phy.Percentage (%) of completion of the Component | [7 empty] | 2206.18
1 | 2 | 3 | 3 | 4 | 5 | 6 | 7 |  |  |  | 4 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | 16 |  | 17 | [8 empty] | 18
1. District Srinagar
1. Executive Engineer Water Supply Master Plan Division Srinagar
1 | Tangnar | 0 | 0 | 928 | 928 | [5 empty] | 928 | CSS (JnNURM) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 928 | 928 |  |  | 928 | 0 | 0 | 0 | 5 | 31.82 | 5 | 27.12 | 3 | 15% | 0 | 2019-06-01 |  |  | 900.88 | Targetted | [9 empty] | Total 40 works to be tendered, out of which 35 No is to be allotted by ending Jan-2019
2 | Sukhnag | 0 | 0 | 1000 | 1000 | [5 empty] | 1000 | CSS (JnNURM) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 1000 | 1000 |  |  | 1000 | 0 | 0 | 0 | 1 | 1.61 | 5 | 1.16 | 1 | 50% | 0 | 2019-06-01 |  |  | 998.84 | Targetted | [9 empty] | 30 No to be tentered and 24 to be allotted by 1st Feb 2019.
3 | Revamping of 4 MGD Water Treatment Plant at Pokhribal | 0 | [8 empty] | Total 4: 61.41; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 5; CSS 10: 2; CSS 11: 3.85; CSS 12: 1; CSS 13: 20%; CSS 14: 0; CSS 15: 2019-09-01 |  |  | 57.56 | Targetted | [9 empty] | 17 No to be tendered and allooted by 15 feb
4 | Construction of State Level Water Testing Laboratory at Zainakote | 0 | [8 empty] | Total 4: 84.36; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 71; CSS 10: 1; CSS 11: 57.69; CSS 12: 1; CSS 13: 60%; CSS 14: 0; CSS 15: 2019-03-01 | 26.67 | Targetted | [11 empty] | work to be alloted on 24 jan 2019
5 | Moomin Abad Khanmoh | 104.59 |  |  | 132.41 | [5 empty] | Total 4: 132.41; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-09-01 |  |  | 132.41 | Targetted | [8 empty] | 0005078358
5 | Total 1 | 104.59 | 0 | 1928 | 2060.41 | 0 | 0 |  |  |  | 2206.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928 | 1928 | 0 | 0 | 1928 | 0 | 0 | 0 | 14 | 109.43 | 13 | 89.82 | 6 |  | 0 |  | 26.67 | 1 | 2089.69 | 4 | [8 empty] | 0 |  |  | 2116.36
2. Executive Engineer Rural Water Supply Division Ganderbal | [57 empty] | 0
1 | Saidpora Drabagh | 0 | 0 | 128.26 | 128.26 | [5 empty] | 128.26 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 128.26 | 128.26 |  |  | 128.26 | 0 | 0 | 0 | 8 | 123.05 | 8 | 120.03 | 5 | 55% |  | 2019-10-01 |  |  | 8.23 | Targetted | [11 empty] | 8.23
2 | Faqir Gujri Dara | 74.83 |  |  | 35 | [5 empty] | Total 4: 35; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 11; CSS 10: 6; CSS 11: 11.5; CSS 12: 6; CSS 13: 30%; CSS 14: nil; CSS 15: 2019-03-01 | 23.5 | Targetted | [10 empty] | 0001777906 |  |  | 23.5
3 | Takiya Sangreshi | 29 |  |  | 24.24 | [5 empty] | Total 4: 24.24; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 6.5; CSS 10: 4; CSS 11: 7; CSS 12: 4; CSS 13: 75%; CSS 14: nil; CSS 15: 2019-03-01 | 17.24 | Targetted | [10 empty] | 0002724062 |  |  | 17.24
3 | Total 2 | 103.83 | 0 | 128.26 | 187.5 | 0 | 0 |  |  |  | 187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128.26 | 128.26 | 0 | 0 | 128.26 | 0 | 0 | 0 | 19 | 140.55 | 18 | 138.53 | 15 |  |  |  | 40.74 | 2 | 8.23 | 1 | [11 empty] | 48.97
3. Executive Engineer Water Works Division Srinagar
1 | Revamping of 10.00 MGD Doodganga WTP, 1.125 MGD Mehjoor Nagar WTP, 6.80 MGD, Alustang WTP, 19.00 MGD Nishat WTP. | 0 |  |  | 973.81 |  | 0 |  |  |  | Total 4: 973.81; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 30; CSS 9: 0; CSS 10: 0; CSS 11: 5; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-09-01 |  |  | 968.81 | Targetted
2 | Improvement and extension of Pipe System Doodhganga and Mehjoornagar System | 0 |  |  | 458.29 |  | 0 |  |  |  | Total 4: 458.29; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 229; CSS 9: 0; CSS 10: 150; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: Shall be completed by Dec-2019 |  |  | 458.29 | Targetted
3 | Improvement and extension of Pipe network of Nishat System | 0 |  |  | 418.22 | [5 empty] | Total 4: 418.22; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0 |  |  | 418.22 | Targetted
4 | Improvemnet and extention of pipe network Alusteng and part of Rangil System | 0 |  |  | 305.55 | [5 empty] | Total 4: 305.55; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0 |  |  | 305.55 | Targetted
4 | Total 3 | 0 | 0 | 0 | 2155.87 | 0 | 0 |  |  |  | 2155.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259 | 0 | 150 | 5 | 0 |  | 0 |  | 0 |  | 2150.87 | 4
12 | Total District Srinagar | 208.42 | 0 | 2056.26 | 4403.78 | 0 | 0 |  |  |  | 4549.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2056.26 | 2056.26 | 0 | 0 | 2056.26 | 0 | 0 | 0 | 292 | 249.98 | 181 | 233.35 | 21 |  | 0 |  | 67.41 | 3 | 4248.79 | 9 | [10 empty] | 4316.2 | 4316.2
2. District Ganderbal
1. Executive Engineer Rural Water Supply Division Ganderbal
1 | Ganderbal Town Phase Ist | 0 | 0 | 75.76 | 75.76 | [5 empty] | 75.76 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 75.76 | 75.76 |  |  | 75.76 | 0 | 0 | 0 | 8 | 35.7 | 4 | 27 | 4 | 45% |  | 2019-12-25 |  |  | 48.76 | Targetted
2 | Shuhama | 0 | 0 | 82.97 | 82.97 | [5 empty] | 82.97 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 82.97 | 82.97 |  |  | 82.97 | 0 | 0 | 0 | 2 | 65 | 5 | 68 | 2 | 90% |  | 2019-12-01 |  |  | 14.97 | Targetted | [9 empty] | remaining 3 No works to be alloted with in 2 days
3 | Ganderbal Town Phase 2nd | 0 | 0 | 222.99 | 222.99 | [5 empty] | 222.99 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 222.99 | 222.99 |  |  | 222.99 | 0 | 0 | 0 | 6 | 36 | 2 | 32 | 2 | 20% |  | 2019-12-30 |  |  | 190.99 | Targetted | [9 empty] | 6 are to be alloted
4 | WSS Re-activation and re-construction of Swajaldhara (Pilot Schemes) | 0 | 0 | 294.27 | 294.27 | [5 empty] | 294.27 | District Sector (Swajadhara)) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 294.27 | 294.27 |  |  | 294.27 | 0 | 0 | 0 | 25 | 125 | 25 | 0 | 0 | 0% | 0 | 2019-12-01 |  |  | 294.27 | Targetted | [9 empty] | work shall be started in March
5 | WSS Kullan | 5 | 0 | 153.64 | 153.64 | [5 empty] | 153.64 | District Sector (Regular) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 153.64 | 153.64 |  |  | 153.64 | 0 | 0 | 0 | 6 | 96 | 6 | 96 | 6 | 60% | 0 | 2019-12-01 |  |  | 57.64 | Targetted | [8 empty] | 0002706221 | To be alloted
6 | Impounding Reservoir for sustainability of 11 No. Water Supply Schemes of Ganderbal and Kangan Constituencies | 215.5 |  |  | 748.23 | [5 empty] | Total 4: 748.23; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0% |  |  | 748.23 | Under process of Designing at Diesgn Directorate | [8 empty] | 0005974489 | Design to be approved Raw water to be commissioned by Sept 2019
7 | Wayil Wudder Gutlibagh | 253.55 |  |  | 50 | [5 empty] | Total 4: 50; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 21; CSS 10: 0; CSS 11: 3; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-09-01 |  |  | 47 | Targetted | [8 empty] | 0001785632 | RSPF to be completed
8 | Kurag Darag Pora |  |  |  | 123.99 | [5 empty] | Total 4: 123.99; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 10; CSS 10: 5; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-10-01 |  |  | 123.99 | Targetted | [9 empty] | Permission is to granted from R&B
9 | Dangerpora Tulmulla | 488.68 |  |  | 92.26 | [5 empty] | Total 4: 92.26; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 6; CSS 9: 9; CSS 10: 6; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-10-01 |  |  | 92.26 | Targetted | [8 empty] | 0002474377 | Permission is to granted from R&B
10 | Gogji Gund | 448 |  |  | 72 | [5 empty] | Total 4: 72; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 15; CSS 10: 3; CSS 11: 0; CSS 12: 3; CSS 13: 0%; CSS 15: 2019-10-01 |  |  | 72 | Targetted | [8 empty] | 0002474401 | For expediting the works for remaining part.
11 | Naqashband Colony Shah Mohalla | 212 |  |  | 88 | [5 empty] | Total 4: 88; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 7; CSS 10: 2; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-10-01 |  |  | 88 | Targetted | [8 empty] | 0002474330 | FSP (Sub-zero) completed by March
11 | Total District Ganderbal | 1622.73 | 0 | 829.63 | 2004.11 | 0 | 0 |  |  |  | 2004.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 829.63 | 829.63 | 0 | 0 | 829.63 | 0 | 0 | 0 | 74 | 419.7 | 58 | 226 | 17 |  | 0 |  |  |  | 1778.11 | 10 | [10 empty] | 1778.11 | 1778.11
3. District Budgam
1. Executive Engineer PHE Division Chadoora
1 | WSS Kuzwera | 361 | 0 | 204.73 | 204.73 | [5 empty] | 204.73 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 204.73 | 204.73 |  |  | 204.73 | 0 | 0 | 0 | 3 | 2.16 | 2 | 0 | 0 | 20% | 0 | 2019-08-01 |  |  | 204.73 | Targetted | [8 empty] | 0005079736 | One work to alloted
2 | Greater Chadura |  | 0 | 700 | 700 | [5 empty] | 700 | State Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 700 | 700 |  |  | 700 | 0 | 0 | 0 | 45 | 141.22 | 29 | 89.47 | 27 | 40% | 2 | 2020-03-01 |  |  | 610.53 | Targetted
3 | WSS Nilnag Hafru | 667 | 0 | 99.01 | 99.01 | [5 empty] | 99.01 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 99.01 | 99.01 |  |  | 99.01 | 0 | 0 | 0 | 6 | 14.08 | 4 | 12.59 | 5 | 10% | 0 | 2019-08-01 |  |  | 86.42 | Targetted | [8 empty] | 0000741378
4 | Pakherpora | 24.33 |  | 182.99 | 182.99 | [5 empty] | Total 4: 182.99; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 182.99; Total 25: 182.99; Total 28: 182.99; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 6; CSS 9: 28.08; CSS 10: 5; CSS 11: 26.18; CSS 12: 6; CSS 13: 30%; CSS 14: 0; CSS 15: 2019-03-01 | 156.81 | Targetted | [10 empty] | 0004746489
5 | Chadoora Town |  |  |  | 266.16 | [5 empty] | Total 4: 266.16; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 0.91; CSS 10: 3; CSS 11: 0.57; CSS 12: 1; CSS 13: 50%; CSS 14: 0; CSS 15: 2019-09-01 |  |  | 265.59 | Targetted
6 | Up- gradation Charishareif Town Phase-II |  |  |  | 785.18 | [5 empty] | Total 4: 785.18; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 12; CSS 9: 163.94; CSS 10: 7; CSS 11: 139.18; CSS 12: 7; CSS 13: 25%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 646 | Targetted
7 | Mir Mohalla Bonpora | 360 |  |  | 184.45 | [5 empty] | Total 4: 184.45; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 61.28; CSS 10: 2; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 184.45 | Targetted | [8 empty] | 0005086386
8 | Handle Bagh | 383 |  |  | 261.61 | [5 empty] | Total 4: 261.61; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 1.53; CSS 10: 0; CSS 11: 3; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 258.61 | Targetted | [8 empty] | 0004705412
8 | Total 1 | 1795.33 | 0 | 1186.73 | 2684.13 | 0 | 0 |  |  |  | 2684.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1186.73 | 1186.73 | 0 | 0 | 1186.73 | 0 | 0 | 0 | 81 | 413.2 | 52 | 270.99 | 46 |  | 2 |  | 156.81 | 1 | 2256.33 | 7 | [10 empty] | 2413.14 | 2413.14
2. Executive Engineer PHE Division Budgam
1 | Laying of common raw water main for (05 NO. water supply schemes Lanilab, Arigam & Bughroo ) | 0 | 0 | 574 | 574 | [5 empty] | 574 | District Sector (Regular) Capex Budget | NIT No-19 PHEDB/civil ,dated:-23.10.2018 | [6 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 574 | 574 |  |  | 574 | 0 | 0 | 0 | 20 | 109 | 15 | 45.39 | 8 | 35% | 0 | 2019-10-01 |  |  | 528.61 | Targetted
2 | Aug. Budgam Town Phase - Ist | 0 | 0 | 76.96 | 76.96 | [5 empty] | 76.96 | District Sector (LIC) | NIT No-19 PHEDB/civil ,dated:-23.10.2018 | [6 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 76.96 | 76.96 |  |  | 76.96 | 0 | 0 | 0 | 3 | 37.83 | 1 | 30 | 1 | 75% | 0 | 2019-03-01 | 46.96 | Targetted | [11 empty] | Reamining 2 No of works to be alloted within weeks time.
3 | Aug. Khanshaib Town | 0 | 0 | 119.1 | 119.1 | [5 empty] | 119.1 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 119.1 | 119.1 |  |  | 119.1 | 0 | 0 | 0 | 6 | 31.54 | 5 | 6.23 | 3 | 40% | 0 | 2019-09-01 |  |  | 112.87 | Targetted
4 | WSS Adina Draripora | 85 | 0 | 159.1 | 159.1 | [5 empty] | 159.1 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 159.1 | 159.1 |  |  | 159.1 | 0 | 0 | 0 | 4 | 41.1 | 2 | 2 | 2 | 40% | 0 | 2019-09-01 |  |  | 157.1 | Targetted | [8 empty] | 0003807192 | Reamining No of works to be alloted within weeks time.
5 | Kathwar | 104 | 0 | 17.85 | 17.85 | [5 empty] | Total 4: 17.58; Total 17: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 17.85; Total 25: 17.85; Total 28: 17.85; MSS 5: 1.49; CSS 6: 13.37; CSS 7: 14.86; CSS 8: 2; CSS 9: 16.2; CSS 10: 2; CSS 11: 17.58; CSS 12: 2; CSS 13: 70%; CSS 14: 1; CSS 15: 2019-03-21 | 0 | Targetted | [10 empty] | 0003967938
6 | Kumar Mohalla Raithan | 245.6 | 0 | 11.31 | 11.31 | [5 empty] | 56.42 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 11.31 | 11.31 |  |  | 11.31 | 0 | 0 | 0 | 3 | 34.8 | 1 | 0 | 1 | 30% | 0 | 2019-06-01 |  |  | 56.42 | Targetted | [8 empty] | 0005359969 | Reamining 2 No of works to be alloted within weeks time.
7 | Lakripora |  | 0 | 137 | 137 | [5 empty] | 34.5 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 137 | 137 |  |  | 137 | 0 | 0 | 0 | 3 | 5.04 | 1 | 0 | 1 | 30% | 0 | 2019-03-01 | 34.5 | Targetted | [11 empty] | Within 10 Days
8 | Nagrad Khah | 92 | 0 | 16.3 | 16.3 | [5 empty] | 16.3 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 16.3 | 16.3 |  |  | 16.3 | 0 | 0 | 0 | 3 | 9.86 | 1 | 0 | 1 | 30% | 0 | 2019-03-01 | 16.3 | Targetted | [10 empty] | 0004729213 | 2 weeks 10 Days
9 | Palar | 0 | 0 | 34.31 | 34.31 | [5 empty] | 49.43 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 34.31 | 34.31 |  |  | 34.31 | 0 | 0 | 0 | 2 | 7.54 | 1 | 0 | 1 | 25% | 0 | 2019-03-01 | 49.43 | Targetted | [11 empty] | 1-10 Days
10 | Qazibagh | 0 | 0 | 25.3 | 25.3 | [5 empty] | 25.3 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 25.3 | 25.3 |  |  | 25.3 | 0 | 0 | 0 | 2 | 3.38 | 1 | 0 | 1 | 20% | 0 | 2019-03-01 | 25.3 | Targetted
11 | Razwan | 0 | 0 | 36.48 | 36.48 | [5 empty] | 36.48 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 36.48 | 36.48 |  |  | 36.48 | 0 | 0 | 0 | 3 | 4.83 | 1 | 0 | 1 | 20% | 0 | 2019-03-01 | 36.48 | Targetted
12 | Ringzibal | 54.71 | 0 | 12.1 | 12.1 | [5 empty] | 12.1 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 12.1 | 12.1 |  |  | 12.1 | 0 | 0 | 0 | 2 | 4.37 | 2 | 0.76 | 2 | 30% | 0 | 2019-03-01 | 11.34 | Targetted | [10 empty] | 0003799945
13 | shamsabad | 151.69 | 0 | 44.17 | 44.17 | [5 empty] | 44.17 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 44.17 | 44.17 |  |  | 44.17 | 0 | 0 | 0 | 1 | 15.64 | 1 | 0 | 1 | 10% | 0 | 2019-03-01 | 44.17 | Targetted | [10 empty] | 0003799863
14 | Sheikhpora | 0 | 0 | 70.7 | 70.7 | [5 empty] | 70.7 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 70.7 | 70.7 |  |  | 70.7 | 0 | 0 | 0 | 2 | 7.9 | 1 | 0 | 1 | 10% | 0 | 2019-06-01 |  |  | 70.7 | Targetted
15 | WSS Kralpora Sofipora | 145 | 0 | 141.1 | 141.1 | [5 empty] | 141.1 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 141.1 | 141.1 |  |  | 141.1 | 0 | 0 | 0 | 4 | 15.88 | 3 | 12.82 | 3 | 50% | 0 | 2019-06-01 |  |  | 128.28 | Targetted | [8 empty] | 0004707220
16 | WSS Mirpora Hayatpora | 47 | 0 | 40.06 | 40.06 | [5 empty] | 42.06 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 40.06 | 40.06 |  |  | 40.06 | 0 | 0 | 0 | 5 | 9.4 | 3 | 1.75 | 3 | 20% | 0 | 2019-06-01 |  |  | 40.31 | Targetted | [8 empty] | 0000684728 | 2 No to be alloted within 10 Days
17 | WSS New Colony Malpora | 72.83 | 0 | 112.04 | 112.04 | [5 empty] | 73 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 112.04 | 112.04 |  |  | 112.04 | 0 | 0 | 0 | 2 | 10.03 | 2 | 7 | 2 | 20% | 0 | 2019-06-01 |  |  | 66 | Targetted | [8 empty] | 0004703140
18 | WSS Sundipora | 222.56 | 0 | 17.44 | 17.44 | [5 empty] | 17.44 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 17.44 | 17.44 |  |  | 17.44 | 0 | 0 | 0 | 4 | 5.51 | 3 | 1.35 | 2 | 20% | 0 | 2019-11-01 |  |  | 16.09 | Targetted | [8 empty] | 0005082016
19 | Magam Narbal | 241 |  |  | 105.6 | [5 empty] | Total 4: 105.6; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 9.34; CSS 10: 2; CSS 11: 1.31; CSS 12: 2; CSS 13: 20%; CSS 14: 0; CSS 15: 2019-06-01 |  |  | 104.29 | Targetted | [8 empty] | 0003975199
20 | Shunglipora Nasserpora | 50 |  |  | 177.12 | [5 empty] | Total 4: 177.12; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 13.47; CSS 10: 3; CSS 11: 0; CSS 12: 2; CSS 13: 10%; CSS 14: 0; CSS 15: 2019-06-01 |  |  | 177.12 | Targetted | [8 empty] | 0004744747
21 | Sonoor Kalipora | 172 |  |  | 68.82 | [5 empty] | Total 4: 68.82; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 3.55; CSS 10: 1; CSS 11: 3.55; CSS 12: 1; CSS 13: 25%; CSS 14: 0; CSS 15: 2019-03-01 | 65.27 | Targetted | [10 empty] | 0002480433
22 | Nowrozbaba Trapai | 0 |  |  | 73 | [5 empty] | Total 4: 73; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 0; CSS 10: 1; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 15: 2019-06-01 |  |  | 73 | Targetted
22 | Total 2 | 1683.39 | 0 | 1645.32 | 2069.86 | 0 | 0 |  |  |  | 1990.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1645.32 | 1645.32 | 0 | 0 | 1645.32 | 1.49 | 13.37 | 14.86 | 80 | 396.21 | 53 | 129.74 | 41 |  | 1 |  | 329.75 | 10 | 1530.79 | 12
30 | Total Budgam District | 3478.72 | 0 | 2832.05 | 4753.99 | 0 | 0 |  |  |  | 4674.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2832.05 | 2832.05 | 0 | 0 | 2832.05 | 1.49 | 13.37 | 14.86 | 161 | 809.41 | 105 | 400.73 | 87 | 0 | 3 | 0 | 486.56 | 11 | 3787.12 | 19 | [10 empty] | 4273.68 | 4273.68
4. District Anantnag
1. Executive Engineer PHE Division Bijbehara
1 | Jablipora | 365 | 0 | 135.69 | 135.69 | [5 empty] | 135.69 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 135.69 | 135.69 |  |  | 135.69 | 0 | 0 | 0 | 2 | 11.41 | 2 | 11.41 | 0 | 0% | 0 | 2019-12-01 |  |  | 124.28 | Targetted | [8 empty] | 0005084391
2 | Kheeribal Rambipora | 300 | 0 | 3323.25 | 3323.25 | [5 empty] | 3291.39 | State Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 3323.25 | 3323.25 |  |  | 3323.25 | 0 | 0 | 0 | 1 | 100 | 1 | 86.7 | 0 | 0% | 0 | 2019-12-01 |  |  | 3204.69 | Targetted | [8 empty] | 0002488701
3 | Checki Isheerdass | 0 | 0 | 259 | 259 | [5 empty] | 259 | State Sector Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 259 | 259 |  |  | 259 | 0 | 0 | 0 | 5 | 77.82 | 5 | 66.36 | 0 | 0% | 0 | 2020-01-01 |  |  | 192.64 | Targetted
4 | Dadoo GB | 0 | 0 | 119.02 | 119.02 | [5 empty] | 119.02 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 119.02 | 119.02 |  |  | 119.02 | 0 | 0 | 0 | 5 | 32.75 | 5 | 30.24 | 0 | 0% | 0 | 2020-01-01 |  |  | 88.78 | Targetted
5 | Beuwora | 0 | 0 | 92.95 | 92.95 | [5 empty] | 92.95 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 92.95 | 92.95 |  |  | 92.95 | 0 | 0 | 0 | 1 | 7 | 1 | 4.26 | 0 | 0% | 0 | 2020-01-01 |  |  | 88.69 | Targetted
6 | Durpora Khiram | 0 | 0 | 115 | 115 | [5 empty] | 115 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 115 | 115 |  |  | 115 | 0 | 0 | 0 | 4 | 35.6 | 4 | 28.28 | 0 | 0% | 0 | 2020-01-01 |  |  | 86.72 | Targetted
7 | Khodpora Khiram | 0 | 0 | 105.34 | 105.34 | [5 empty] | 105.34 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 105.34 | 105.34 |  |  | 105.34 | 0 | 0 | 0 | 4 | 33.65 | 4 | 25.2 | 0 | 0% | 0 | 2019-12-01 |  |  | 80.14 | Targetted
8 | Batpora Bijbehara Goriwan | 0 | 0 | 112.25 | 112.25 | [5 empty] | 112.25 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 112.25 | 112.25 |  |  | 112.25 | 0 | 0 | 0 | 1 | 19 | 1 | 9.17 | 0 | 0% | 0 | 2019-12-01 |  |  | 103.08 | Targetted
9 | Kokernag Garden (Junk of Pipes) | 240 | 0 | 491.25 | 491.25 | [5 empty] | 491.25 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 491.25 | 491.25 |  |  | 491.25 | 3.5 | 20 | 23.5 | 3 | 52.6 | 0 | 0 | 0 | 0% | 0 | 2020-01-01 |  |  | 491.25 | Targetted | [8 empty] | 0006450955
10 | Seer - Ist | 0 | 0 | 383.83 | 383.83 | [5 empty] | 383.83 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 383.83 | 383.83 |  |  | 383.83 | 0 | 0 | 0 | 2 | 43.23 | 2 | 31.48 | 0 | 0% | 0 | 2020-01-01 |  |  | 352.35 | Targetted
11 | Krangsoo | 0 | 0 | 381.82 | 381.82 | [5 empty] | 381.82 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 381.82 | 381.82 |  |  | 381.82 | 0 | 0 | 0 | 3 | 49.3 | 3 | 39.03 | 0 | 0% | 0 | 2020-01-01 |  |  | 342.79 | Targetted
12 | Andoo Pushroo | 499 |  |  | 391.36 | [5 empty] | Total 4: 391.36; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 7.24; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2020-01-01 |  |  | 391.36 | Targetted | [8 empty] | 0062488272
13 | Anantnag Town (High Ground) | 0 |  |  | 256.81 | [5 empty] | Total 4: 256.81; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-11-01 |  |  | 256.81 | Targetted
14 | Daksum GB | 70 |  |  | 135.36 | [5 empty] | Total 4: 135.36; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 135.36 | Targetted | [8 empty] | 0005392496
15 | Chaklipora | 37.5 |  |  | 29.27 | [5 empty] | Total 4: 29.27; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 6.6; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2020-01-01 |  |  | 29.27 | Targetted | [8 empty] | 0000773377
16 | Up-gradation of Achabal Town. | 0 |  |  | 465.17 | [5 empty] | Total 4: 465.17; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-11-01 |  |  | 465.17 | Targetted
17 | Sheikhpora matipora | 0 |  |  | 163.01 | [5 empty] | Total 4: 163.01; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 72.57; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 163.01 | Targetted
18 | Inderan Gradader | 0 | [8 empty] | Total 4: 85.82; MSS 5: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2020-01-01 |  |  | 85.82 | Targetted
19 | Mammal | 0 | [8 empty] | Total 4: 329.16; MSS 5: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-11-01 |  |  | 329.16 | Targetted
20 | Arigole | 2 | [8 empty] | Total 4: 143.28; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 143.28 | Targetted | [8 empty] | 0000773246
21 | Kralpora Laripora | 0 | [8 empty] | Total 4: 142.88; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-11-01 |  |  | 142.88 | Targetted
22 | Fohar Batapora | 16.76 | 0 | 528.34 | 528.34 | [5 empty] | 528.34 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 528.34 | 528.34 |  |  | 528.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 2019-12-01 |  |  | 528.34 | Targetted | [8 empty] | 0000773492
22 | Total 1 | 1530.26 | 0 | 6047.74 | 7488.72 | 0 | 0 |  |  |  | 8158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6047.74 | 6047.74 | 0 | 0 | 6047.74 | 3.5 | 20 | 23.5 | 41 | 548.77 | 28 | 332.13 | 0 |  | 0 |  |  | 0 | 7825.87 | 22
2. Executive Engineer PHE Division Qazigund
1 | Bragam | 60 | 0 | 23.5 | 23.5 | [5 empty] | 23.5 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 23.5 | 23.5 |  |  | 23.5 | 0 | 0 | 0 | 4 | 22.3 | 5 | 21.85 | 4 | 60% | 2 | 2019-03-01 | 1.65 | Targetted | [10 empty] | 0000704055
2 | Levodara Kachipora | 191 | 0 | 154.67 | 154.67 | [5 empty] | 154.67 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 154.67 | 154.67 |  |  | 154.67 | 3 | 27.44 | 30.44 | 8 | 93 | 5 | 85.4 | 4 | 60% | nil | 2019-07-01 |  |  | 69.27 | Targetted
3 | Saidwara Lift | 172.3 | 0 | 88.56 | 88.56 | [5 empty] | 88.56 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 88.56 | 88.56 |  |  | 88.56 | 0.75 | 6.79 | 7.54 | 8 | 32 | 8 | 35.2 | 8 | 70% | 2 | 2019-03-01 | 53.36 | Targetted
4 | Ziarat Sharief Chohan | 47.16 | 0 | 40 | 40 | [5 empty] | 40 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 40 | 40 |  |  | 40 | 0 | 0 | 0 | 5 | 34 | 3 | 32 | 2 | 40% | 1 | 2019-04-01 |  |  | 8 | Targetted | [8 empty] | 0005647492
5 | Rajard Dooniwari | 181 | 0 | 135.75 | 135.75 | [5 empty] | 135.75 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 135.75 | 135.75 |  |  | 135.75 | 3 | 24.44 | 27.44 | 6 | 90 | 6 | 89.4 | 6 | 50% | 2 | 2019-03-01 | 46.35 | Targetted | [10 empty] | 0004754176
6 | N C Sadoora | 187 | 0 | 197.47 | 197.47 | [5 empty] | 127.47 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 197.47 | 197.47 |  |  | 197.47 | 70 | 70 | 140 | 4 | 45.5 | 3 | 35 | 2 | 30% | 1 | 2019-09-01 |  |  | 92.47 | Targetted | [8 empty] | 0002712875
7 | G.B.Checki Drabihal | 91.92 |  | 47.59 | 47.59 | [5 empty] | Total 4: 47.59; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 47.59; Total 25: 47.59; Total 28: 47.59; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 39.5; CSS 10: 2; CSS 11: 24; CSS 12: 2; CSS 13: 30%; CSS 14: nil; CSS 15: 2019-07-01 |  |  | 23.59 | Targetted | [8 empty] | 0005794386
8 | Aug.Agnoo | 240 |  | 68.69 | 68.69 | [5 empty] | Total 4: 68.69; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 68.69; Total 25: 68.69; Total 28: 68.69; MSS 5: 0; CSS 6: 95.38; CSS 7: 95.38; CSS 8: 3; CSS 9: 20.5; CSS 10: 3; CSS 11: 23.2; CSS 12: 2; CSS 13: 40%; CSS 14: nil; CSS 15: 2019-05-01 |  |  | 45.49 | Targetted | [8 empty] | 0005395933
9 | Qamer Thamankote | 24 |  | 20 | 20 | [5 empty] | Total 4: 34; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 20; Total 25: 20; Total 28: 20; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 30.2; CSS 10: 5; CSS 11: 27.3; CSS 12: 5; CSS 13: 60%; CSS 14: nil; CSS 15: 2019-03-01 | 6.7 | Targetted | [10 empty] | 0000817111
10 | Additional OHT for Gassipora | 106.49 | 0 | 52.55 | 52.55 | [5 empty] | 52.6 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 52.55 | 52.55 |  |  | 52.55 | 0 | 0 | 0 | 6 | 52 | 5 | 48.4 | 4 | 70% | nil | 2019-03-01 | 4.2 | Targetted | [10 empty] | 0000786410
11 | Furah Zaroora | 200 |  | 14.87 | 14.87 | [5 empty] | Total 4: 15; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 14.87; Total 25: 14.87; Total 28: 14.87; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 6; CSS 9: 13.5; CSS 10: 5; CSS 11: 12.2; CSS 12: 4; CSS 13: 60%; CSS 14: 1; CSS 15: 2019-03-01 | 2.8 | Targetted | [10 empty] | 0004754149
12 | Dudwangan | 0 |  | 18.5 | 18.5 | [5 empty] | Total 4: 18.5; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 18.5; Total 25: 18.5; Total 28: 18.5; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 17.2; CSS 10: 5; CSS 11: 15.3; CSS 12: 5; CSS 13: 70%; CSS 14: 2; CSS 15: 2019-03-01 | 3.2 | Targetted
13 | Kokagund | 100 |  | 10.67 | 10.67 | [5 empty] | Total 4: 10.67; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 10.67; Total 25: 10.67; Total 28: 10.67; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 10.3; CSS 10: 3; CSS 11: 6.3; CSS 12: 3; CSS 13: 45%; CSS 14: nil; CSS 15: 2019-03-01 | 4.37 | Targetted | [10 empty] | 0003818987
14 | panzoo Lift | 91.68 |  | 20.69 | 20.69 | [5 empty] | Total 4: 20.69; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 20.69; Total 25: 20.69; Total 28: 20.69; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 16.3; CSS 10: 3; CSS 11: 15.4; CSS 12: 3; CSS 13: 70%; CSS 14: nil; CSS 15: 2019-02-01 | 5.29 | Targetted | [10 empty] | 0005392851
15 | Augmentaion Larkipora | 250 |  |  | 285.33 | [5 empty] | Total 4: 285.33; MSS 5: 0; CSS 6: 37; CSS 7: 37; CSS 8: 6; CSS 9: 135; CSS 10: 5; CSS 11: 85; CSS 12: 4; CSS 13: 40%; CSS 14: nil; CSS 15: 2019-09-30 |  |  | 200.33 | Targetted | [8 empty] | 0005647430
16 | Augmentaion Qazigund | 181 |  |  | 282.38 | [5 empty] | Total 4: 282.38; MSS 5: 0; CSS 6: 27.44; CSS 7: 27.44; CSS 8: 8; CSS 9: 220; CSS 10: 7; CSS 11: 217; CSS 12: 4; CSS 13: 30%; CSS 14: nil; CSS 15: 2019-10-01 |  |  | 65.38 | Targetted
17 | Hiller Shabad | 460 |  |  | 254.11 | [5 empty] | Total 4: 254.11; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 130; CSS 10: 7; CSS 11: 130; CSS 12: 6; CSS 13: 60%; CSS 14: 2; CSS 15: 2019-05-01 |  |  | 124.11 | Targetted | [8 empty] | 0004754271
18 | Aug.Doru | 0 |  |  | 302.5 | [5 empty] | Total 4: 302.5; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 96; CSS 10: 3; CSS 11: 86; CSS 12: 3; CSS 13: 30%; CSS 14: nil; CSS 15: 2019-10-01 |  |  | 216.5 | Targetted
19 | Ziarat Sharief Matipora | 198 |  |  | 88 | [5 empty] | Total 4: 88; MSS 5: 0; CSS 6: 24.38; CSS 7: 24.38; CSS 8: 4; CSS 9: 80; CSS 10: 4; CSS 11: 82.4; CSS 12: 1; CSS 13: 10%; CSS 14: nil; CSS 15: 2019-07-01 |  |  | 5.6 | Targetted | [8 empty] | 0005086466
20 | Divisional Office Building at Qazigund | 0 |  |  | 138.51 | [5 empty] | Total 4: 138.51; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 35; CSS 10: 3; CSS 11: 35; CSS 12: 2; CSS 13: 30%; CSS 14: nil; CSS 15: 2019-10-01 |  |  | 103.51 | Targetted
21 | Lalan Ganoor | 0 |  | 77 | 77 | [5 empty] | Total 4: 91.12; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 77; Total 25: 77; Total 28: 77; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 74.5; CSS 10: 2; CSS 11: 8.5; CSS 12: 2; CSS 13: 20%; CSS 14: nil; CSS 15: 2019-08-01 |  |  | 82.62 | Targetted
22 | Chirhama Bogam | 0 |  | 112.78 | 112.78 | [5 empty] | Total 4: 112.18; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 112.78; Total 25: 112.78; Total 28: 112.78; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 9; CSS 9: 90.3; CSS 10: 8; CSS 11: 93.5; CSS 12: 7; CSS 13: 50%; CSS 14: 2; CSS 15: 2019-05-01 |  |  | 18.68 | Targetted
23 | Reshipora Gawas | 55 | [8 empty] | Total 4: 20; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 21; CSS 10: 4; CSS 11: 20; CSS 12: 4; CSS 13: 65%; CSS 14: 2; CSS 15: 2019-03-01 | 0 | Targetted | [10 empty] | 0004754379
23 | Total 2 | 2836.55 | 0 | 1083.29 | 2434.12 | 0 | 0 |  |  |  | 2411.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083.29 | 1083.29 | 0 | 0 | 1083.29 | 76.75 | 312.87 | 389.62 | 128 | 1398.1 | 104 | 1228.35 | 87 |  | 17 |  | 127.92 | 10 | 1055.55 | 13
45 | Total District Anantnag | 4366.81 | 0 | 7131.03 | 9922.84 | 0 | 0 |  |  |  | 10569.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7131.03 | 7131.03 | 0 | 0 | 7131.03 | 80.25 | 332.87 | 413.12 | 169 | 1946.87 | 132 | 1560.48 | 87 |  | 17 |  | 127.92 | 10 | 8881.42 | 35 | [8 empty] | 0 |  | 9009.34 | 9009.34
5. District Kulgam
1. Executive Engineer Special PHE Division Kulgam
1 | Chellan Narsingpora | 0 | 0 | 157.87 | 157.87 | [5 empty] | 157.87 | District Sector (Regular) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 157.87 | 157.87 |  |  | 157.87 | 0 | 0 | 0 | 3 | 9.1 | 3 | 10 | 3 | 45% |  | 2019-12-01 |  |  | 147.87 | Targetted
2 | Widow Mishpora | 0 | 0 | 199.5 | 199.5 | [5 empty] | 200.59 | District Sector (Regular) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 199.5 | 199.5 |  |  | 199.5 | 0 | 0 | 0 | 2 | 13 | 2 | 0 | 2 | 30% |  | 2019-12-01 |  |  | 200.59 | Targetted
3 | Pazipora | 59 | 0 | 74.77 | 74.77 | [5 empty] | 74.77 | District Sector (Regular) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 74.77 | 74.77 |  |  | 74.77 | 0 | 0 | 0 | 13 | 26.68 | 3 | 10 | 3 | 30% |  | 2019-12-01 |  |  | 64.77 | Targetted | [8 empty] | 0003979684
4 | Nardpora autoo | 32.16 | 0 | 77.11 | 77.11 | [5 empty] | 76.83 | District Sector (Regular) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 77.11 | 77.11 |  |  | 77.11 | 0 | 0 | 0 | 7 | 6.21 | 1 | 2 | 1 | 25% |  | 2019-12-01 |  |  | 74.83 | Targetted | [8 empty] | 0005360245
5 | Lassipora Laisoo | 30.09 | 0 | 109.8 | 109.8 | [5 empty] | 109.8 | District Sector (Regular) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 109.8 | 109.8 |  |  | 109.8 | 0 | 0 | 0 | 16 | 23.29 | 1 | 3 | 1 | 40% |  | 2019-12-01 |  |  | 106.8 | Targetted | [8 empty] | 0001766125
6 | Zradoo Gujjar Basti | 0 | 0 | 136.41 | 136.41 | [5 empty] | 136.41 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 136.41 | 136.41 |  |  | 136.41 | 0 | 0 | 0 | 1 | 6.23 | 1 | 7 | 1 | 45% |  | 2019-12-01 |  |  | 129.41 | Targetted
7 | Brazloo Tengen | 0 | 0 | 232.71 | 232.71 | [5 empty] | 232.71 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 232.71 | 232.71 |  |  | 232.71 | 0 | 0 | 0 | 2 | 17.84 | 1 | 4 | 1 | 60% |  | 2019-12-01 |  |  | 228.71 | Targetted
8 | WSS Malwan G.B | 0 | 0 | 36.45 | 36.45 | [5 empty] | 36.18 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 36.45 | 36.45 |  |  | 36.45 | 0 | 0 | 0 | 2 | 22.26 | 0 | 0 | 0 | 0% |  | 2019-12-01 |  |  | 36.18 | Targetted
9 | WSS Die Mohalla Gulabpathri | 0 | 0 | 60.22 | 60.22 | [5 empty] | 60.11 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 60.22 | 60.22 |  |  | 60.22 | 0 | 0 | 0 | 4 | 3.91 | 0 | 0 | 0 | 0% |  | 2019-12-01 |  |  | 60.11 | Targetted
10 | Yaripora | 21.65 | 0 | 53.67 | 53.67 | [5 empty] | 53.67 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 53.67 | 53.67 |  |  | 53.67 | 0 | 0 | 0 | 3 | 12 | 3 | 15.5 | 2 | 60% |  | 2019-12-01 |  |  | 38.17 | Targetted | [8 empty] | 0003819207
11 | Banimulla Gujjer Basti | 30.67 | 0 | 106.86 | 106.86 | [5 empty] | Total 4: 106.86; Total 17: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 106.86; Total 25: 106.86; Total 28: 106.86; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-12-01 |  |  | 106.86 | Targetted | [8 empty] | 0001984026
12 | Budroo Dembdulla | 225 | 0 | 55.64 | 55.64 | [5 empty] | Total 4: 55.64; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 55.64; Total 25: 55.64; Total 28: 55.64; MSS 5: 2.66; CSS 6: 33.62; CSS 7: 36.28; CSS 8: 2; CSS 9: 14.5; CSS 10: 2; CSS 11: 15.5; CSS 12: 1; CSS 13: 80%; CSS 15: 2019-03-01 | 40.14 | Targetted | [10 empty] | 0005060025
13 | Chandgree | 144.9 | 0 | 45 | 45 | [5 empty] | Total 4: 45; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 45; Total 25: 45; Total 28: 45; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 10.5; CSS 10: 1; CSS 11: 6.5; CSS 12: 1; CSS 13: 80%; CSS 15: 2019-01-01 | 38.5 | Targetted | [10 empty] | 0004709737
14 | Damhall | 281 | 0 | 91.05 | 91.05 | [5 empty] | Total 4: 91.05; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 91.05; Total 25: 91.05; Total 28: 91.05; MSS 5: 7.61; CSS 6: 68.45; CSS 7: 76.06; CSS 8: 7; CSS 9: 27; CSS 10: 5; CSS 11: 25; CSS 12: 7; CSS 13: 40%; CSS 15: 2019-03-01 | 66.05 | Targetted | [10 empty] | 0005080806
15 | Hakwas KB Pora | 195.25 | 0 | 128.15 | 128.15 | [5 empty] | Total 4: 128.15; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 128.15; Total 25: 128.15; Total 28: 128.15; MSS 5: 3.83; CSS 6: 34.43; CSS 7: 38.26; CSS 8: 7; CSS 9: 23.55; CSS 10: 3; CSS 11: 20; CSS 12: 3; CSS 13: 35%; CSS 15: 2019-12-01 |  |  | 108.15 | Targetted | [8 empty] | 0005083783
16 | Kulgam Town | 0 | 0 | 403.67 | 403.67 | [5 empty] | Total 4: 323.67; Total 17: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 403.67; Total 25: 403.67; Total 28: 403.67; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-12-01 |  |  | 323.67 | Targetted
17 | Nasu | 39 | 0 | 38.01 | 38.01 | [5 empty] | Total 4: 38.01; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 38.01; Total 25: 38.01; Total 28: 38.01; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 4; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-03-01 | 38.01 | Targetted | [10 empty] | 0005793711
18 | Sarsuna Tantraypora | 171 | 0 | 90.32 | 90.32 | [5 empty] | Total 4: 90.32; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 90.32; Total 25: 90.32; Total 28: 90.32; MSS 5: 34.32; CSS 6: 0; CSS 7: 34.32; CSS 8: 2; CSS 9: 19.5; CSS 10: 2; CSS 11: 19.5; CSS 12: 2; CSS 13: 70%; CSS 15: 2019-03-01 | 70.82 | Targetted | [10 empty] | 0005087111
19 | Shalipora Tarigam | 229.6 | 0 | 75.24 | 75.24 | [5 empty] | Total 4: 75.24; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 75.24; Total 25: 75.24; Total 28: 75.24; MSS 5: 0; CSS 6: 47.84; CSS 7: 47.84; CSS 8: 2; CSS 9: 5.23; CSS 10: 1; CSS 11: 1.75; CSS 12: 1; CSS 13: 80%; CSS 15: 2019-12-01 |  |  | 73.49 | Targetted | [8 empty] | 0004709317
20 | Soper Daneu | 219.35 | 0 | 58.51 | 58.51 | [5 empty] | Total 4: 58.51; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 58.51; Total 25: 58.51; Total 28: 58.51; MSS 5: 0; CSS 6: 8.51; CSS 7: 8.51; CSS 8: 1; CSS 9: 11.22; CSS 10: 1; CSS 11: 12; CSS 12: 1; CSS 13: 50%; CSS 15: 2019-03-01 | 46.51 | Targetted | [10 empty] | 0004710181
21 | Vovrikhull | 207.69 | 0 | 90.71 | 90.71 | [5 empty] | Total 4: 90.71; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 90.71; Total 25: 90.71; Total 28: 90.71; MSS 5: 2.06; CSS 6: 18.54; CSS 7: 20.6; CSS 8: 16; CSS 9: 18.88; CSS 10: 4; CSS 11: 10; CSS 12: 4; CSS 13: 45%; CSS 15: 2019-03-01 | 80.71 | Targetted | [10 empty] | 0004710133
22 | WSS Gophbal Kawkibazar | 173 | 0 | 128.15 | 128.15 | [5 empty] | Total 4: 60; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 128.15; Total 25: 128.15; Total 28: 128.15; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 9.45; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 15: 2019-03-01 | 60 | Targetted | [10 empty] | 0005087214
23 | Sunigam | 127.85 |  |  | 44.6 | [5 empty] | Total 4: 44.6; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 15: 2019-02-01 | 44.6 | Targetted | [10 empty] | 0005663439
23 | Total ( 1 ) :- | 2187.21 | 0 | 2449.82 | 2494.42 | 0 | 0 |  |  |  | 2346.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2449.82 | 2449.82 | 0 | 0 | 2449.82 | 50.48 | 211.39 | 261.87 | 100 | 284.35 | 34 | 161.75 | 34 |  |  |  | 485.34 | 9 | 1699.61 | 14
2. Executive Engineer PHE Division Qazigund
1 | Additional OHT for WSS Kharman Ganish | 62.45 | 0 | 30 | 30 | [5 empty] | 30 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 30 | 30 |  |  | 30 | 0 | 0 | 0 | 6 | 26 | 6 | 26.5 | 2 | 40% | 1 | 2019-03-01 | 3.5 | Targetted | [10 empty] | 0005794393
2 | Chowgam Gundipora | 154 | 0 | 9.68 | 9.68 | [5 empty] | Total 4: 9.68; Total 17: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 9.68; Total 25: 9.68; Total 28: 9.68; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 7; CSS 10: 1; CSS 11: 2; CSS 12: 1; CSS 13: 30%; CSS 14: nil; CSS 15: 2019-05-01 |  |  | 7.68 | Targetted | [8 empty] | 0005795654
3 | Kral Check | 85.48 | 0 | 35 | 35 | [5 empty] | Total 4: 35; Total 17: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 35; Total 25: 35; Total 28: 35; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 31.4; CSS 10: 3; CSS 11: 30.2; CSS 12: 3; CSS 13: 70%; CSS 14: 1; CSS 15: 2019-03-01 | 4.8 | Targetted | [10 empty] | 0002486290
4 | Vessu Manigam | 146.66 | 0 | 44.31 | 44.31 | [5 empty] | Total 4: 44.32; Total 17: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 44.31; Total 25: 44.31; Total 28: 44.31; MSS 5: 9.26; CSS 6: 0; CSS 7: 9.26; CSS 8: 4; CSS 9: 37.25; CSS 10: 3; CSS 11: 25.3; CSS 12: 2; CSS 13: 60%; CSS 14: nil; CSS 15: 2019-03-01 | 19.02 | Targetted | [10 empty] | 0005794567
5 | Gundi Tankipora | 299 | 0 | 16.91 | 16.91 | [5 empty] | Total 4: 16.86; Total 17: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 16.91; Total 25: 16.91; Total 28: 16.91; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 15.45; CSS 10: 2; CSS 11: 15.85; CSS 12: 2; CSS 13: 45%; CSS 14: nil; CSS 15: 2019-03-01 | 1.01 | Targetted | [10 empty] | 0005087257
6 | Aug.Razloo | 0 |  | 47.17 | 47.17 | [5 empty] | Total 4: 47.37; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 47.17; Total 25: 47.17; Total 28: 47.17; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 46.5; CSS 10: 5; CSS 11: 46.5; CSS 12: 3; CSS 13: 70%; CSS 14: 1; CSS 15: 2019-03-01 | 0.87 | Targetted
7 | Kral Kanchloo | 78.49 |  | 120.4 | 120.4 | [5 empty] | Total 4: 120.14; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 120.4; Total 25: 120.4; Total 28: 120.4; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 115.3; CSS 10: 5; CSS 11: 110.3; CSS 12: 3; CSS 13: 50%; CSS 14: nil; CSS 15: 2019-07-01 |  |  | 9.84 | Targetted | [8 empty] | 0003819710
7 | Total 2 :- | 826.08 | 0 | 303.47 | 303.47 | 0 | 0 |  |  |  | 303.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 303.47 | 303.47 | 0 | 0 | 303.47 | 9.26 | 0 | 9.26 | 29 | 278.9 | 25 | 256.65 | 16 |  | 3 |  | 29.2 | 5 | 17.52 | 2
30 | Total District Kulgam | 3013.29 | 0 | 2753.29 | 2797.89 | 0 | 0 |  |  |  | 2650.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2753.29 | 2753.29 | 0 | 0 | 2753.29 | 59.74 | 211.39 | 271.13 | 129 | 563.25 | 59 | 418.4 | 50 | 0 | 3 | 0 | 514.54 | 14 | 1717.13 | 16 | [10 empty] | 2231.67 | 2231.67
6. District Pulwama
1. Executive Engineer PHE Division Awantipora
1 | Aug. Pampore | 0 | 0 | 68.5 | 68.5 | [5 empty] | 68.5 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 68.5 | 68.5 |  |  | 68.5 | 0 | 0 | 0 | 3 | 12.06 | 3 | 8.72 | 2 | 30% | 0 | 2019-03-01 | 59.78 | Targetted
2 | Aug. Tral | 337.45 | 0 | 74.2 | 74.2 | [5 empty] | 74.2 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 74.2 | 74.2 |  |  | 74.2 | 0 | 0 | 0 | 6 | 31.23 | 6 | 25.32 | 0 | 0% | 0 | 2019-06-01 |  |  | 48.88 | Targetted | [8 empty] | 0005257240
3 | Augmentaion Awantipora Town | 0 | 0 | 124.18 | 124.18 | [5 empty] | 124.18 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 124.18 | 124.18 |  |  | 124.18 | 0 | 0 | 0 | 4 | 6.278 | 0 | 0 | 0 | 0% | 0 | 2019-03-01 |  |  | 124.18 | Targetted
4 | Gujar Basti Wahab Sahib | 8.99 | 0 | 24.92 | 24.92 | [5 empty] | 24.92 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 24.92 | 24.92 |  |  | 24.92 | 0 | 0 | 0 | 4 | 7.422 | 1 | 2.9 | 0 | 0% | 0 | 2019-02-01 | 22.02 | Targetted | [10 empty] | 0005084223
5 | Gulshan pora Kharpora | 268.65 | 0 | 24.74 | 24.74 | [5 empty] | 24.74 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 24.74 | 24.74 |  |  | 24.74 | 0 | 0.07 | 0.07 | 6 | 9.633 | 6 | 1.83 | 2 | 5% | 0 | 2019-03-01 | 22.91 | Targetted | [10 empty] | 0003994199
6 | Pahal Dajan | 167.86 | 0 | 26 | 26 | [5 empty] | 26 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 26 | 26 |  |  | 26 | 0 | 0 | 0 | 11 | 18.325 | 11 | 6.5 | 0 | 0% | 0 | 2019-03-01 | 19.5 | Targetted | [10 empty] | 0005057317
7 | Marvel | 190 |  |  | 205.25 | [5 empty] | Total 4: 205.25; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 6; CSS 9: 22.138; CSS 10: 2; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-09-01 |  |  | 205.25 | Targetted | [8 empty] | 0004963377
8 | Aluchibagh | 0 |  |  | 287.42 | [5 empty] | Total 4: 287.42; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 14.188; CSS 10: 5; CSS 11: 5; CSS 12: 0; CSS 13: 10%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 282.42 | Targetted
9 | Batapora (Ladu) | 0 |  |  | 88.94 | [5 empty] | Total 4: 88.94; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 9; CSS 9: 27.42; CSS 10: 9; CSS 11: 0; CSS 12: 2; CSS 13: 15%; CSS 14: 0; CSS 15: 2019-03-01 | 88.94 | Targetted
10 | Water Supply to AIIMS at Awantipora | 0 |  |  | 848.6 | [5 empty] | Total 4: 848.6; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 62.005; CSS 10: 2; CSS 11: 79.92; CSS 12: 1; CSS 13: 5%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 768.68 | Targetted
10 | Total | 972.95 | 0 | 342.54 | 1772.75 | 0 | 0 |  |  |  | 1772.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342.54 | 342.54 | 0 | 0 | 342.54 | 0 | 0.07 | 0.07 | 55 | 210.699 | 45 | 130.19 | 7 |  | 0 |  | 213.15 | 5 | 1429.41 | 5
2. Executive Engineer PHE Division Pulwama | [54 empty] | 7
1 | Pinglina | 0 | 0 | 25 | 25 | [5 empty] | 25 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 25 | 25 |  |  | 25 | 0 | 0 | 0 | 2 | 4.5 | 2 | 4.5 | 2 | 90% | 0 | 2019-03-01 | 20.5 | Targetted
2 | Gundipora | 166.5 | 0 | 23.33 | 23.33 | [5 empty] | 23.33 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 23.33 | 23.33 |  |  | 23.33 | 0 | 0 | 0 | 1 | 2.05 | 1 | 2.05 | 1 | 30% | 0 | 2019-06-01 |  |  | 21.28 | Targetted | [8 empty] | 0001766489
3 | Shakerpora Dadoora | 122.5 |  |  | 219.07 | [5 empty] | Total 4: 219.07; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 85.8; CSS 10: 5; CSS 11: 0; CSS 12: 5; CSS 13: 50%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 219.07 | Targetted | [8 empty] | 0001722745
4 | Parigam | 249.5 |  |  | 12.6 | [5 empty] | Total 4: 12.6; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 3.99; CSS 10: 2; CSS 11: 0; CSS 12: 2; CSS 13: 60%; CSS 14: 0; CSS 15: 2019-03-01 | 12.6 | Targetted | [10 empty] | 0001722891
5 | Drasoo Chatripora | 299 |  |  | 125.41 | [5 empty] | Total 4: 125.41; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 11.49; CSS 10: 0; CSS 11: 0; CSS 12: 1; CSS 13: 45%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 125.41 | Targetted | [8 empty] | 0002489365 | Well in Progress commisioned by 15th Feb
6 | Augmentaion Pulwama Town | 0 |  |  | 129.75 | [5 empty] | Total 4: 129.75; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 111.57; CSS 10: 0; CSS 11: 0; CSS 12: 5; CSS 13: 40%; CSS 14: 2; CSS 15: 2019-06-01 |  |  | 129.75 | Targetted
7 | Machpona | 144.54 |  |  | 40 | [5 empty] | Total 4: 40; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 0; CSS 10: 1; CSS 11: 0; CSS 12: 0; CSS 13: 30%; CSS 14: 0; CSS 15: 2019-09-01 |  |  | 40 | Targetted | [8 empty] | 0002489888
8 | Planpora Nayana | 274.5 |  |  | 39 | [5 empty] | Total 4: 39; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 13; CSS 10: 2; CSS 11: 13; CSS 12: 2; CSS 13: 60%; CSS 14: 0; CSS 15: 2019-03-01 | 26 | Targetted | [10 empty] | 0002686730
9 | Adipora Trichal | 165 |  |  | 59 | [5 empty] | Total 4: 59; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 37.73; CSS 10: 2; CSS 11: 37.73; CSS 12: 2; CSS 13: 60%; CSS 14: 0; CSS 15: 2019-03-01 | 21.27 | Targetted | [10 empty] | 0002489947
10 | Mirbugh Dogam | 200 |  |  | 228 | [5 empty] | Total 4: 228; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 0; CSS 10: 1; CSS 11: 0; CSS 12: 0; CSS 13: 45%; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 228 | Targetted | [8 empty] | 0005062346
11 | Gulbugh | 266.78 |  |  | 139.2 | [5 empty] | Total 4: 139.32; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 14: 0; CSS 15: 2019-12-01 |  |  | 139.32 | Targetted | [8 empty] | 0005058267
12 | Zaipora | 359 |  |  | 295.59 | [5 empty] | Total 4: 46; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 22.15; CSS 10: 2; CSS 11: 22.15; CSS 12: 1; CSS 13: 80%; CSS 14: 0; CSS 15: 2019-03-01 | 23.85 | Targetted | [10 empty] | 0002644179
13 | Shadimarg | 210 |  |  | 73.5 | [5 empty] | Total 4: 73.5; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 31.12; CSS 10: 1; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-04-01 |  |  | 73.5 | Targetted | [8 empty] | 0005087014
14 | Saidpora Dangerpora | 151 | 0 | 21 | 21 | [5 empty] | 21 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 21 | 21 |  |  | 21 | 0 | 0 | 0 | 2 | 2.17 | 1 | 0.67 | 0 | 30% | 0 | 2019-03-01 | 20.33 | [11 empty] | 0005086990
15 | Kakapora |  |  |  | 137.19 | [5 empty] | Total 4: 137.19; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 54.27; CSS 10: 2; CSS 11: 0; CSS 12: 1; CSS 13: 55%; CSS 14: 0; CSS 15: 2019-06-01 |  |  | 137.19 | Targetted | [8 empty] | 0006542970
15 | Total | 2608.32 | 0 | 69.33 | 1567.64 | 0 | 0 |  |  |  | 1318.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69.33 | 69.33 | 0 | 0 | 69.33 | 0 | 0 | 0 | 33 | 379.84 | 22 | 80.1 | 22 |  |  |  | 124.55 | 6 | 1113.52 | 9
25 | Total District Pulwama | 3581.27 | 0 | 411.87 | 3340.39 | 0 | 0 |  |  |  | 3090.92 | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | 88 | 590.539 | 67 | 210.29 | 29 | 0 | 0 | 0 | 337.7 | 11 | 2542.93 | 14 | [10 empty] | 2880.63 | 2880.63
7. District Shopian
1. Executive Engineer PHE Division Shopian
1 | Nowgam Rangmarg | 437 | 0 | 40 | 40 | [5 empty] | 40 | CSS (NRDWP) | 05/PHS of 2018-19 dated:-06-07-2018 | [6 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 40 | 40 |  |  | 40 | 4.06 | 36.52 | 40.58 | 4 | 11.73 | 4 | 11.73 | 1 | 20% | 0 | 2019-03-01 | 28.27 | Targetted | [10 empty] | 0001670997
2 | Kral Mohalla Vishroo | 434.87 | 0 | 30 | 30 | [5 empty] | 29.13 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 30 | 30 |  |  | 30 | 0 | 0 | 0 | 3 | 16.57 | 3 | 16.57 | 1 | 10% | 0 | 2019-03-01 | 12.56 | Targetted | [10 empty] | 0002490705
3 | Gatipora Dachnoo | 482.5 | 0 | 151 | 151 | [5 empty] | 151 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 151 | 151 |  |  | 151 | 0 | 0 | 0 | 17 | 33.28 | 10 | 33.28 | 2 | 25% | 0 | 2019-09-01 |  |  | 117.72 | Targetted | [8 empty] | 0002490737
4 | Karewa Safnagri | 250 | 0 | 60 | 60 | [5 empty] | 60 | CSS (NRDWP) | Already tendered . | [6 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 60 | 60 |  |  | 60 | 0 | 0 | 0 | 3 | 54.95 | 3 | 54.95 | 1 | 70% | 0 | 2019-03-01 | 5.05 | Targetted | [10 empty] | 0003985228
5 | Tulran Tachloo | 107 | 0 | 53 | 53 | [5 empty] | 53 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 53 | 53 |  |  | 53 | 0 | 0 | 0 | 2 | 5.38 | 2 | 3.38 | 0 | 0% | 0 | 2019-03-01 | 49.62 | Targetted | [10 empty] | 0005082184
6 | Vasoohallan | 497 | 0 | 121 | 121 | [5 empty] | 121 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 121 | 121 |  |  | 121 | 0 | 0 | 0 | 4 | 20.71 | 4 | 20.71 | 0 | 0% | 0 | 2019-07-01 | 100.29 | Targetted | [10 empty] | 0002490993
7 | Doompora | 149.6 | 0 | 149 | 149 | [5 empty] | 149 | CSS (NRDWP) | 09/PHS of 2018 dated:- 15-09-2018 | [6 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 149 | 149 |  |  | 149 | 0 | 0 | 0 | 2 | 40.56 | 2 | 40.56 | 1 | 20% | 0 | 2019-09-01 |  |  | 108.44 | Targetted | [8 empty] | 0001670919
8 | Shirmal Sherpathri | 798 | 0 | 112.86 | 112.86 | [5 empty] | 112.66 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 112.86 | 112.86 |  |  | 112.86 | 0 | 0 | 0 | 10 | 29.8 | 10 | 29.08 | 1 | 20% | 0 | 2019-10-01 |  |  | 83.58 | Targetted | [8 empty] | 0002491052
8 | Total District Shopian | 3155.97 | 0 | 716.86 | 716.86 | 0 | 0 |  |  |  | 715.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716.86 | 716.86 | 0 | 0 | 716.86 | 4.06 | 36.52 | 40.58 | 45 | 212.98 | 38 | 210.26 | 7 |  | 0 |  | 195.79 | 5 | 309.74 | 3 | [10 empty] | 505.53 | 505.53
8. District Baramulla
1. Executive Engineer PHE Division Baramulla
1 | Hill top Ushkura | 0 | 0 | 257.26 | 257.26 | [5 empty] | 219.9 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 257.26 | 257.26 |  |  | 257.26 | 0 | 0 | 0 | 5 | 52.51 | 4 | 31.7 | 3 | 25% | 0 | 2019-10-01 |  |  | 188.2 | Targetted
2 | Bandi Bala | 117.35 | 0 | 96.28 | 96.28 | [5 empty] | 96.28 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 96.28 | 96.28 |  |  | 96.28 | 0 | 0 | 0 | 5 | 34.95 | 3 | 19.32 | 3 | 50% | 0 | 2019-10-01 |  |  | 76.96 | Targetted | [8 empty] | 0005087500
3 | Bandi Payeen | 113.7 | 0 | 60 | 60 | [5 empty] | 60 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 60 | 60 |  |  | 60 | 0 | 0 | 0 | 3 | 24.49 | 2 | 19.91 | 2 | 10% | 0 | 2019-10-01 |  |  | 40.09 | Targetted | [8 empty] | 0002724610
4 | Dangerpora | 0 | 0 | 24.94 | 24.94 | [5 empty] | 24.94 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 24.94 | 24.94 |  |  | 24.94 | 0 | 0 | 0 | 4 | 20.49 | 3 | 13.78 | 0 | 0% | 0 | 2019-03-01 | 11.16 | Targetted
5 | Hardkul Paldaji | 174 | 0 | 20 | 20 | [5 empty] | 20 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 20 | 20 |  |  | 20 | 0 | 0 | 0 | 3 | 13.12 | 2 | 5.49 | 0 | 0% | 0 | 2019-03-01 | 14.51 | Targetted | [10 empty] | 0005058428
6 | Kawhar Kalibal | 248.72 | 0 | 20 | 20 | [5 empty] | 20 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 20 | 20 |  |  | 20 | 0 | 0 | 0 | 3 | 11.57 | 1 | 2.38 | 0 | 0% | 0 | 2019-10-01 |  |  | 17.62 | Targetted | [8 empty] | 0002480247
7 | Malsooma | 85.12 | 0 | 18 | 18 | [5 empty] | 18 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 18 | 18 |  |  | 18 | 0 | 0 | 0 | 2 | 7.62 | 1 | 3.82 | 0 | 0% | 0 | 2019-03-01 | 14.18 | Targetted | [10 empty] | 0005397822
8 | Nilsar Baldaji | 196.9 | 0 | 30.57 | 30.57 | [5 empty] | 30.57 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 30.57 | 30.57 |  |  | 30.57 | 0 | 0.59 | 0.59 | 3 | 9.74 | 3 | 8.88 | 3 | 30% | 0 | 2019-03-01 | 21.69 | Targetted | [10 empty] | 0003995110
9 | Veederabad | 225 | 0 | 243.25 | 243.25 | [5 empty] | 243.75 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 243.25 | 243.25 |  |  | 243.25 | 0 | 60 | 60 | 3 | 64.75 | 1 | 2.25 | 1 | 10% | 0 | 2019-10-01 |  |  | 241.5 | Targetted | [8 empty] | 0005795681
10 | Zamzampora | 225 | 0 | 60 | 60 | [5 empty] | 60 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 60 | 60 |  |  | 60 | 0 | 0 | 0 | 6 | 40.43 | 2 | 12.81 | 0 | 0% | 0 | 2019-10-01 |  |  | 47.19 | Targetted | [8 empty] | 0001716091
11 | Karewa Astanpora OHT | 149 | 0 | 146 | 146 | [5 empty] | 146 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 146 | 146 |  |  | 146 | 6.66 | 59.98 | 66.64 | 5 | 81.26 | 4 | 79.45 | 3 | 40% | 0 | 2019-10-01 |  |  | 66.55 | Targetted | [8 empty] | 0006427803
12 | Mukdampora | 149 | 0 | 257.9 | 257.9 | [5 empty] | 257.9 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 257.9 | 257.9 |  |  | 257.9 | 0 | 0 | 0 | 4 | 28.31 | 3 | 28.31 | 1 | 30% | 0 | 2019-10-01 |  |  | 229.59 | Targetted | [8 empty] | 0006476766
13 | Dolipora Fresthar | 451.28 |  |  | 104.03 | [5 empty] | Total 4: 104.03; MSS 5: 6.94; CSS 6: 62.49; CSS 7: 69.43; CSS 8: 5; CSS 9: 68; CSS 10: 2; CSS 11: 11; CSS 12: 2; CSS 13: 80%; CSS 14: 0; CSS 15: 2019-03-01 | 93.03 | Targetted | [10 empty] | 0001985774
14 | Khushalpora Syed Colony Chinned | 451.28 |  |  | 743.43 | [5 empty] | Total 4: 743.43; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 120; CSS 10: 5; CSS 11: 108; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 635.43 | Targetted | [8 empty] | 0004717505
15 | Mongam Wagoora | 455 |  |  | 169.43 | [5 empty] | Total 4: 169.43; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 45; CSS 10: 2; CSS 11: 9.5; CSS 12: 2; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 159.93 | Targetted | [8 empty] | 0004714271
16 | New Colony Maharajpora | 195 |  |  | 741.45 | [5 empty] | Total 4: 741.45; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 70; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 741.45 | Targetted | [8 empty] | 0004717581
17 | Syed janbaz wali Khanpora | 188 |  |  | 172 | [5 empty] | Total 4: 172; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 106.5; CSS 10: 1; CSS 11: 4.35; CSS 12: 1; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 167.65 | Targetted | [8 empty] | 0005795009
18 | Khadniyar jalsheeri | 353.75 |  |  | 66 | [5 empty] | Total 4: 66; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 10.95; CSS 10: 2; CSS 11: 8; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 58 | Targetted | [8 empty] | 0005058457
19 | Watergam Behrampora | 254 |  |  | 468.72 | [5 empty] | Total 4: 468.72; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 54.99; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 468.72 | Targetted | [8 empty] | 0000883736
20 | Malganipora Behrampora | 144 |  |  | 149.7 | [5 empty] | Total 4: 149.7; MSS 5: 0; CSS 6: 19.72; CSS 7: 19.72; CSS 8: 5; CSS 9: 155.25; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 149.7 | Targetted | [8 empty] | 0003881252
21 | Kiterdaji Kangroosa | 241 |  |  | 209 | [5 empty] | Total 4: 209; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 130.2; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 209 | Targetted | [8 empty] | 0002480388
22 | Ladi Angan | 112.6 |  |  | 102.4 | [5 empty] | Total 4: 102.4; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 7.95; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 102.4 | Targetted | [8 empty] | 0001716104
23 | Venkura | 0 |  |  | 166 | [5 empty] | Total 4: 166; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 55.99; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 166 | Targetted
24 | Laiser Hadipora | 0 |  |  | 202.83 | [5 empty] | Total 4: 202.83; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 21.73; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 202.83 | Targetted
25 | Jahama | 354 |  |  | 139.58 | [5 empty] | Total 4: 139.58; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 23.36; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-03-01 | 139.58 | Targetted | [10 empty] | 0006327483
26 | Jetty | 0 |  |  | 203 | [5 empty] | Total 4: 203; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 180; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 203 | Targetted
27 | Gujjer Pati Bhat Mohalla Sangri | 324.73 |  |  | 99.48 | [5 empty] | Total 4: 99.48; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 40.92; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 99.48 | Targetted | [8 empty] | 0005816658
28 | Hyder Mohalla Singh bagh | 150 |  |  | 200 | [5 empty] | Total 4: 200; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 102.64; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 200 | Targetted | [8 empty] | 0005397907
29 | Alsafa Colony | 195 |  |  | 255 | [5 empty] | Total 4: 255; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 185.88; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 255 | Targetted | [8 empty] | 0005058564
30 | Chuker adjoing areas | 307 |  |  | 224.85 | [5 empty] | Total 4: 224.85; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 26.91; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 224.85 | Targetted | [8 empty] | 0003995880
31 | Dandosa Doligund | 92 |  |  | 458 | [5 empty] | Total 4: 458; MSS 5: 6.54; CSS 6: 58.83; CSS 7: 65.37; CSS 8: 7; CSS 9: 288; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 458 | Targetted | [8 empty] | 0004756064
31 | Total | 5952.43 | 0 | 1234.2 | 6109.1 | 0 | 0 |  |  |  | 6072.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1234.2 | 1234.2 | 0 | 0 | 1234.2 | 20.14 | 261.61 | 281.75 | 117 | 2083.51 | 41 | 368.95 | 21 | 0% | 0 |  | 294.15 | 6 | 5409.14 | 25
2. Executive Engineer PHE Division Sopore
1 | Nathipora Wadora | 59.59 | 0 | 8.39 | 8.39 | [5 empty] | 8.39 | CSS (NRDWP) | NIT No-11 dated:-19.10.2018 | [6 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 8.39 | 8.39 |  |  | 8.39 | 0 | 0 | 0 | 1 | 8 | 1 | 8.4 | 1 | 80% | 0 | 2019-03-01 | -0.01 | Targetted | [10 empty] | 0002712928
2 | Ningli Amberpora | 75.4 | 0 | 13.93 | 13.93 | [5 empty] | 13.93 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 13.93 | 13.93 |  |  | 13.93 | 0 | 0 | 0 | 1 | 14.21 | 1 | 16.83 | 1 | 15% | 0 | 2019-03-01 | -2.9 | Targetted | [10 empty] | 0000683837
3 | Mahrajpora Sopore | 78.28 | 0 | 94.5 | 94.5 | [5 empty] | 94.55 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 94.5 | 94.5 |  |  | 94.5 | 0 | 0 | 0 | 3 | 19 | 3 | 18.5 | 3 | 60% | 0 | 2019-03-01 | 76.05 | Targetted | [10 empty] | 0006169820
4 | Sheer Colony Sopore | 0 | 0 | 38.5 | 38.5 |  | 0 |  |  |  | 38.5 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 38.5 | 38.5 |  |  | 38.5 | 0 | 0 | 0 | 4 | 12 | 4 | 12.6 | 3 | 50% | 0 | 2019-05-01 |  |  | 25.9 | Targetted
5 | Chechpora Nowpora | 130.34 | 0 | 26.12 | 26.12 | [5 empty] | Total 4: 26.12; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 26.12; Total 25: 26.12; Total 28: 26.12; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 6; CSS 9: 9.5; CSS 10: 1; CSS 11: 1.75; CSS 12: 1; CSS 15: 2019-03-01 | 24.37 | Targetted | [10 empty] | 0005818592
6 | Sidiq Colony Sopore | 164.31 | 0 | 217.4 | 217.4 | [5 empty] | 109.62 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 217.4 | 217.4 |  |  | 217.4 | 0 | 0 | 0 | 5 | 45 | 3 | 32 | 2 | 20% | 0 | 2019-08-01 |  |  | 77.62 | Targetted | [8 empty] | 0005087609
7 | Ningli Gath | 259 |  |  | 315.76 | [5 empty] | Total 4: 315.76; MSS 5: 0; CSS 6: 24.47; CSS 7: 24.47; CSS 8: 2; CSS 9: 25; CSS 10: 2; CSS 11: 25.1; CSS 12: 2; CSS 13: 40%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 290.66 | Targetted | [8 empty] | 0006548447
8 | Daribal Amberpora | 698 |  |  | 787.86 | [5 empty] | Total 4: 787.86; MSS 5: 0; CSS 7: 0; CSS 8: 4; CSS 9: 154; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 787.86 | Targetted | [8 empty] | 0005818554
9 | Foodpark Colony | 210 |  |  | 400.2 | [5 empty] | Total 4: 402.66; MSS 5: 19.44; CSS 6: 174.96; CSS 7: 194.4; CSS 8: 1; CSS 9: 18; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 402.66 | Targetted | [8 empty] | 0005797367
10 | Rakhi Hygam Haritar | 246.83 | [8 empty] | Total 4: 295.59; MSS 5: 0; CSS 6: 37.52; CSS 7: 37.52; CSS 8: 1; CSS 9: 4; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 295.59 | Targetted | [8 empty] | 0005795854
11 | Zainageer | 0 | 0 | 610.08 | 610.08 | [5 empty] | 655.58 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 610.08 | 610.08 |  |  | 610.08 | 0 | 0 | 0 | 2 | 124 | 2 | 103.95 | 2 | 10% | 0 | 2019-05-01 |  |  | 551.63 | Targetted
12 | Yamberzalwari | 0 | 0 | 110 | 110 | [5 empty] | 118 | District Sector (Regular) Capex Budget | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 110 | 110 |  |  | 110 | 0 | 0 | 0 | 4 | 14.85 | 0 | 0 | 0 | 0% | 0 | Oc-19 |  |  | 118 | Targetted
12 | Total | 1921.75 | 0 | 1118.92 | 2622.74 | 0 | 0 |  |  |  | 2866.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1118.92 | 1118.92 | 0 | 0 | 1118.92 | 19.44 | 236.95 | 256.39 | 34 | 447.56 | 17 | 219.13 | 15 |  | 0 |  | 97.51 | 4 | 2549.92 | 8
3. Executive Engineer Hyd. Division Uri
1 | Salamabad (Nowpora) | 145 | 0 | 34.62 | 34.62 | [5 empty] | 34.73 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 34.62 | 34.62 |  |  | 34.62 | 0 | 0 | 0 | 5 | 12.28 | 4 | 9.0057 | 0 | 0% | 0 | 2019-03-01 | 25.7243 | Targetted | [10 empty] | 0005796570
2 | Basian Dachi | 57.98 |  |  | 27.3 | [5 empty] | Total 4: 33.26; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 6.04; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 33.26 | Targetted | [8 empty] | 0005005513
3 | Rampora | 74.32 |  |  | 301.7 | [5 empty] | Total 4: 30.4; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 10.52; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-03-01 | 30.4 | Targetted | [10 empty] | 0001787724
4 | Kamalkote | 136.42 |  |  | 788.6 | [5 empty] | Total 4: 76.09; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 5.83; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 76.09 | Targetted | [8 empty] | 0001752918
5 | Sabai Gohallan | 139.23 |  |  | 462.1 | [5 empty] | Total 4: 52.18; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 5.8; CSS 10: 1; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 52.18 | Targetted | [8 empty] | 0004718211
6 | Dadyali Puranpllan | 123.7 |  |  | 26.1 | [5 empty] | Total 4: 26.11; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 21.54; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 26.11 | Targetted | [8 empty] | 0004718230
7 | Bandi kamalkote | 65.9 |  |  | 473.4 | [5 empty] | Total 4: 49.9; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 49.9 | Targetted | [8 empty] | 0005088430
8 | Panjinag | 123.78 |  |  | 618.3 | [5 empty] | Total 4: 61.92; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 13.15; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 61.92 | Targetted | [8 empty] | 0004718180
9 | Maidanan Boniyar | 108.22 |  |  | 292 | [5 empty] | Total 4: 44.11; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 20.96; CSS 10: 3; CSS 11: 18.01; CSS 12: 3; CSS 13: 45%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 26.1 | Targetted | [8 empty] | 0005088439
10 | Noorkhah Kanchan | 97.29 | [8 empty] | Total 4: 85.82; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 0.67; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 85.82 | Targetted | [8 empty] | 0005088468
11 | Khunjidi Khodi Nambla | 58.59 | [8 empty] | Total 4: 339.16; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 339.16 | Targetted | [8 empty] | 0005396359
12 | Sultan Daki | 50 | [8 empty] | Total 4: 143.28; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 143.28 | Targetted | [8 empty] | 0001666267
13 | Saidpora | 0 | [8 empty] | Total 4: 142.94; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 142.94 | Targetted
14 | Churanda Batgran | 0 | [8 empty] | Total 4: 216.85; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 216.85 | Targetted
15 | Gingle | 0 | [8 empty] | Total 4: 61.42; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 61.42 | Targetted
16 | Bijhama Niloosa | 117.74 | [8 empty] | Total 4: 84.36; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 84.36 | Targetted | [8 empty] | 0001716109
16 | Total | 1298.17 | 0 | 34.62 | 3024.12 | 0 | 0 |  |  |  | 1482.53 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.62 | 34.62 | 0 | 0 | 34.62 | 0 | 0 | 0 | 23 | 96.79 | 8 | 27.0157 | 3 | 45% | 0 |  | 56.1243 | 2 | 1399.39 | 14
4. Executive Engineer FBI Division Tangmarg
1 | Kunzer Town | 0 |  |  | 165 | [5 empty] | Total 4: 165; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 33.67; CSS 10: 4; CSS 11: 23.47; CSS 12: 3; CSS 13: 30%; CSS 15: 2019-03-01 | 141.53 | Targetted
2 | Kampora Solinda Qazipora | 143 |  |  | 20.69 | [5 empty] | Total 4: 20.69; MSS 5: 0; CSS 6: 30.07; CSS 7: 30.07; CSS 8: 3; CSS 9: 18.47; CSS 10: 3; CSS 11: 14.75; CSS 12: 3; CSS 13: 50%; CSS 15: 2019-03-01 | 5.94 | Targetted | [10 empty] | 0005797012
3 | Ravamping of Filtration Plants in PHED Tangmarg | 0 | [8 empty] | Total 4: 79.87; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 38; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-03-01 | 79.87 | Targetted
4 | Improvement/Extension/ Replacement of Damaged pipes for various closed WSS of PHE SD Tangmarg | 0 | [8 empty] | Total 4: 293; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 29; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 15: 2019-10-01 |  |  | 293 | Targetted
4 | Total | 143 | 0 | 4775.48 | 23697.61 | 0 | 0 |  |  |  | 558.56 | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 30.07 | 30.07 | 18 | 119.14 | 7 | 38.22 | 6 |  | 0 |  | 227.34 | 3 | 293 | 1
63 | Total District Baramulla | 9315.35 | 0 | 7163.22 | 35453.57 | 0 | 0 |  |  |  | 10979.89 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 39.58 | 528.63 | 568.21 | 192 | 2747 | 73 | 653.3157 | 45 | 653.3157 | 0 |  | 675.1243 | 15 | 9651.45 | 48 | [10 empty] | 10326.5743 | 10326.5743
9. District Bandipora
1. Executive Engineer Hyd. Division Bandipora
1 | Tangath | 112 | 0 | 14.16 | 14.16 | [5 empty] | 14.16 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 14.16 | 14.16 |  |  | 14.16 | 0 | 0 | 0 | 2 | 7.38 | 2 | 5.97 | 2 | 50% | 0 | 2019-03-01 | 8.19 | Targetted | [10 empty] | 0004725200
2 | Pannar | 162.83 | 0 | 22 | 22 | [5 empty] | 21.1 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 22 | 22 |  |  | 22 | 0 | 0 | 0 | 2 | 10.36 | 2 | 7.13 | 2 | 50% | 0 | 2019-03-01 | 13.97 | Targetted | [10 empty] | 0004963848
3 | Maliknard Gurnar | 0 |  |  | 24.5 | [5 empty] | Total 4: 24.5; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 10.54; CSS 10: 3; CSS 11: 7.53; CSS 12: 3; CSS 13: 30%; CSS 14: 0; CSS 15: 2019-03-01 | 16.97 | Targetted
4 | Patushai Degree Colleger | 335 | [8 empty] | Total 4: 399.45; MSS 5: 0; CSS 6: 68.4; CSS 7: 68.4; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 399.45 | Targetted | [8 empty] | 0004714230
5 | Source Promotion Bandipora | 625 | [8 empty] | Total 4: 152.98; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 152.98 | Targetted | [8 empty] | 0005087980
6 | Heeven Colony Nishatbagh | 563 | [8 empty] | Total 4: 262.91; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 262.91 | Targetted | [8 empty] | 0004714286
7 | Construction of 0.65 MGD RSFP & 1.25 gallon SR for WSS Bandipora | 0 | [8 empty] | Total 4: 186; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 186 | Targetted
8 | Barladi Darpora | 0 | [8 empty] | Total 4: 369.21; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 369.21 | Targetted | [10 empty] | 1409.68 | 1409.68
8 | Total | 1797.83 | 0 | 36.16 | 60.66 | 0 | 0 |  |  |  | 1430.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.16 | 36.16 | 0 | 0 | 36.16 | 0 | 68.4 | 68.4 | 7 | 28.28 | 7 | 20.63 | 7 |  | 0 |  | 39.13 | 3 | 1370.55 | 5
2. Executive Engineer PHE Division Sopore
1 | Gundi Khalil Ganastan | 43.27 | 0 | 14.11 | 14.11 | [5 empty] | 14.11 | CSS (NRDWP) | NIT NO-11 dated:- 19.10.2018 | [6 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 14.11 | 14.11 |  |  | 14.11 | 0 | 0 | 0 | 1 | 14 | 1 | 13.86 | 1 | 30% |  | 2019-03-01 | 0.25 | Targetted | [10 empty] | 0004749922
2 | Well at Odena | 64.36 | 0 | 36.06 | 36.06 | [5 empty] | 36.06 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 36.06 | 36.06 |  |  | 36.06 | 0 | 0 | 0 | 1 | 20 | 1 | 18.3 | 1 | 20% |  | 2019-03-01 | 17.76 | Targetted | [10 empty] | 0005794531
3 | Nesbal | 0 | 0 | 47.46 | 47.46 | [5 empty] | 47.46 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 47.46 | 47.46 |  |  | 47.46 | 0 | 0 | 0 | 2 | 34 | 2 | 32 | 1 | 50% |  | 2019-03-01 | 15.46 | Targetted
4 | Malpora Tengpora | 210.79 | 0 | 63 | 63 | [5 empty] | 63 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 63 | 63 |  |  | 63 | 0 | 0 | 0 | 1 | 45 | 1 | 44 | 1 | 40% |  | 2019-05-01 |  |  | 19 | Targetted | [8 empty] | 0002476913
5 | Sumbal Town | 0 | 0 | 138.99 | 138.99 | [5 empty] | 138.99 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 138.99 | 138.99 |  |  | 138.99 | 0 | 0 | 0 | 3 | 30 | 3 | 29 | 2 | 10% |  | 2019-10-01 |  |  | 109.99 | Targetted
6 | Hajan Town | 0 | 0 | 336.75 | 336.75 | [5 empty] | 336.75 | District Sector (LIC) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 336.75 | 336.75 |  |  | 336.75 | 0 | 0 | 0 | 2 | 80 | 2 | 73 | 1 | 15% |  | 2019-10-01 |  |  | 263.75 | Targetted
7 | Batagund | 274 | 0 | 289.2 | 289.2 | [5 empty] | Total 4: 15; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 289.2; Total 25: 289.2; Total 28: 289.2; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 15; CSS 10: 1; CSS 11: 13.8; CSS 12: 1; CSS 13: 20%; CSS 15: 2019-03-01 | 1.2 | Targetted | [10 empty] | 0004728198
8 | Hajin Chndergeer | 0 |  |  | 54.8 | [5 empty] | Total 4: 54.88; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 45.5; CSS 10: 1; CSS 11: 41.88; CSS 12: 1; CSS 15: 2019-03-01 | 13 | Targetted
8 | Total | 592.42 | 0 | 925.57 | 980.37 | 0 | 0 |  |  |  | 706.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 925.57 | 925.57 | 0 | 0 | 925.57 | 0 | 0 | 0 | 12 | 283.5 | 12 | 265.84 | 9 |  | 0 |  | 47.67 | 5 | 392.74 | 3 | [10 empty] | 440.41 | 440.41
3. Executive Engineer Special PHE Sub Division Guraz
1 | Khuprihajin | 0 | [8 empty] | Total 4: 42.3; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 42.3 | Targetted
2 | Purana Tullail | 0 | [8 empty] | Total 4: 59.67; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 59.67 | Targetted
3 | Tetron Khotron | 33 | [8 empty] | Total 4: 61.07; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 61.07 | Targetted | [8 empty] | 0005084653
4 | Burnaio | 0 | [8 empty] | Total 4: 39.31; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 39.31 | Targetted
5 | Bosgay Refugee | 10 | [8 empty] | Total 4: 103.78; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 103.78 | Targetted | [8 empty] | 0004750475
6 | Bodoab | 0 | [8 empty] | Total 4: 104.13; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 104.13 | Targetted
7 | Kilshay | 0 | [8 empty] | Total 4: 57.42; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 57.42 | Targetted
8 | Kilisari Bagtoor | 0 | [8 empty] | Total 4: 60; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 60 | Targetted
9 | Mir Mohalla Gujran | 0 | [8 empty] | Total 4: 155.86; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 155.86 | Targetted
10 | Churwan | 0 | [8 empty] | Total 4: 86; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 86 | Targetted
11 | Hassangam Malangam | 0 | [8 empty] | Total 4: 72.11; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 72.11 | Targetted
12 | Neeru Short | 105.86 | [8 empty] | Total 4: 293.92; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 293.92 | Targetted | [8 empty] | 0005084515
13 | Badugam | [9 empty] | Total 4: 200.02; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 200.02 | Targetted
13 | Total | 148.86 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1335.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  | 0 | 0 | 1335.59 | 13
29 | Total District Bandipora | 2539.11 | 0 | 961.73 | 1041.03 | 0 | 0 |  |  |  | 3472.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 961.73 | 961.73 | 0 | 0 | 961.73 | 0 | 68.4 | 68.4 | 19 | 311.78 | 19 | 286.47 | 16 | 0% | 0 | 0 | 86.8 | 8 | 3098.88 | 21 | [11 empty] | 3185.68 | 3185.68
10. District Kupwara
1. Executive Engineer PHE Division Kupwara
1 | WSS Khaithan | 0 | 0 | 140.28 | 140.28 | [5 empty] | 140.28 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 140.28 | 140.28 |  |  | 140.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 |  |  |  | 140.28 | Targetted
2 | WSS Upper munwan | 0 | 0 | 202 | 202 | [5 empty] | 202 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 202 | 202 |  |  | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | - |  |  | 202 | Targetted
3 | WSS Mohi gund rangwar lalpora | 0 | 0 | 75.29 | 75.29 | [5 empty] | 75.29 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 75.29 | 75.29 |  |  | 75.29 | 0 | 0 | 0 | 6 | 30.5 | 3 | 14.2 | 2 | 70% | - | 2019-03-01 | 61.09 | Targetted
4 | Lashtiyal Kalaroos | 0 | 0 | 1267.2 | 1267.2 | [5 empty] | 1267.2 | CSS (NRDWP) | [7 empty] | 0 |  | 0 |  |  | 0 | 0 | 1267.2 | 1267.2 |  |  | 1267.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | - |  |  | 1267.2 | Targetted
5 | Kupwara Town | 0 | 0 | 534.44 | 534.44 | [5 empty] | 534.44 | CSS (NRDWP) | [7 empty] | 0 |  | 0 |  |  | 0 | 0 | 534.44 | 534.44 |  |  | 534.44 | 0 | 0 | 0 | 4 | 28.5 | 4 | 25.45 | 2 | 70% | - | 2019-01-01 | 508.99 | Targetted
6 | Short Muqami Kooligam | 0 | 0 | 649.28 | 649.28 | [5 empty] | 649.28 | CSS (NRDWP) | [7 empty] | 0 |  | 0 |  |  | 0 | 0 | 649.28 | 649.28 |  |  | 649.28 | 0 | 0 | 0 | 3 | 9 | 3 | 7 | 1 | 30% | - | 2019-03-01 | 642.28 | Targetted
7 | Gangbugh | 0 | 0 | 376.73 | 376.73 | [5 empty] | 376.73 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 376.73 | 376.73 |  |  | 376.73 | 0 | 0 | 0 | 3 | 25.3 | 2 | 17.2 | 2 | 60% | - | 2019-03-01 | 359.53 | Targetted
8 | Wavoora Maidanpora | 252.72 |  |  | 60 | [5 empty] | Total 4: 60; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 6; CSS 9: 16.2; CSS 10: -; CSS 11: 7.1; CSS 12: 1; CSS 13: 30%; CSS 14: -; CSS 15: 2019-03-01 | 52.9 | Targetted | [10 empty] | 0001716158
9 | Sogam | 0 |  |  | 285.95 | [5 empty] | Total 4: 285.95; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 54.2; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0 |  |  | 285.95 | Targetted
10 | Dedsun Bala | 0 |  |  | 95.95 | [5 empty] | Total 4: 95.95; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: -; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 95.95 | Targetted
11 | Gagal | 195.65 |  |  | 230 | [5 empty] | Total 4: 230; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 6.32; CSS 10: 2; CSS 11: 4.25; CSS 12: 0; CSS 13: 0; CSS 14: 0 |  |  | 225.75 | Targetted | [8 empty] | 0001716170
12 | Rangnard Bala | 45.88 |  |  | 394 | [5 empty] | Total 4: 39.4; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 33.2; CSS 10: 2; CSS 11: 24.45; CSS 12: 0; CSS 13: 0; CSS 14: 0 |  |  | 14.95 | Targetted | [8 empty] | 0005081822
13 | Halpal DC Office complex Kupwara | 300.85 |  |  | 90 | [5 empty] | Total 4: 90; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 33; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 90 | Targetted | [8 empty] | 0002672076
14 | Guziyal | 81 |  |  | 147 | [5 empty] | Total 4: 147; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: -; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0 |  |  | 147 | Targetted | [8 empty] | 0004728538
15 | Khangund | 70.61 |  |  | 59.39 | [5 empty] | Total 4: 59.39; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: -; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 59.39 | Targetted | [8 empty] | 0005087099
16 | Jamgund Gujjerpati | 0 |  |  | 690 | [5 empty] | Total 4: 69; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 21.2; CSS 10: 1; CSS 11: 6; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 63 | Targetted
17 | Sheikh Pora Sani | 152 |  |  | 860 |  | 86 |  |  |  | Total 4: 86; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 7; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 86 | Targetted | [8 empty] | 0002476717
18 | Manigah | 112.38 |  |  | 67 | [5 empty] | Total 4: 67; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 8; CSS 9: 51.2; CSS 10: 8; CSS 11: 55; CSS 12: 4; CSS 13: 55%; CSS 14: -; CSS 15: 2019-03-01 | 12 | Targetted | [10 empty] | 0000695542
19 | Mathipora Dardpora | 0 |  |  | 730.8 | [5 empty] | Total 4: 73.08; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 13.35; CSS 10: 1; CSS 11: 8.45; CSS 12: 1; CSS 13: 70%; CSS 14: -; CSS 15: 2019-03-01 | 64.63 | Targetted
20 | Soner pora Mirwayen | 773.49 | [8 empty] | Total 4: 47; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0 |  |  | 47 | Targetted | [8 empty] | 0005720524
21 | Batridi Lolab | 43.7 |  |  | 524.6 | [5 empty] | Total 4: 52.46; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 19.2; CSS 10: 2; CSS 11: 10.62; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 41.84 | Targetted | [8 empty] | 0005082056
22 | Kharpati GB Dardpora | 16.72 |  |  | 18 | [5 empty] | Total 4: 18; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 17.5; CSS 10: -; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 18 | Targetted | [8 empty] | 0005082011
23 | Madmadovrang | 92 |  |  | 520.6 | [5 empty] | Total 4: 52.06; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: -; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 52.06 | Targetted | [8 empty] | 0005101993
24 | Banjarpati Bandibala | 16.7 |  |  | 657.5 | [5 empty] | Total 4: 65.75; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 0; CSS 9: 0; CSS 10: 0; CSS 11: 0; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 65.75 | Targetted | [8 empty] | 0005082396
25 | Rakhi Gund Manchar | 38.1 |  |  | 152.2 | [5 empty] | Total 4: 150.22; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 31.45; CSS 10: 1; CSS 11: 21; CSS 12: 0; CSS 13: 0; CSS 14: 0; CSS 15: - |  |  | 129.22 | Targetted | [8 empty] | 0001723069
26 | Malik Mohalla Gratnard | 45.88 | 0 | 43.02 | 43.02 | [5 empty] | 43.02 | CSS (NRDWP) | [7 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 43.02 | 43.02 |  |  | 43.02 | 0 | 0 | 0 | 3 | 25.3 | 2 | 17.2 | 2 | 60% | - | 2019-03-01 | 25.82 | Targetted | [10 empty] | 0005081832
27 | Palnard Chandigam | 39.4 |  |  |  |  | 15.54 |  |  |  | Total 4: 15.54; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 11.15; CSS 10: 1; CSS 11: 7; CSS 12: 0; CSS 13: 0; CSS 14: 0 |  |  | 8.54 | Targetted | [8 empty] | 0005081915
27 | Total | 2277.08 | 0 | 3288.24 | 8871.23 | 0 | 101.54 |  |  |  | 4992.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3288.24 | 3288.24 | 0 | 0 | 3288.24 | 0 | 0 | 0 | 67 | 433.57 | 32 | 224.92 | 15 |  | 0 |  | 1727.24 | 8 | 3039.88 | 19
2. Executive Engineer PHE Division Handwara
1 | Dohama | 65 | 0 | 51.85 | 51.85 | [5 empty] | 51.85 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 51.85 | 51.85 |  |  | 51.85 | 0 | 72.2 | 72.2 | 4 | 18.82 | 4 | 8.22 | 4 | 100% | 3 | 2019-02-01 | 43.63 | Targetted | [10 empty] | 0006181331
2 | Dudhkul | 17.5 | 0 | 43.8 | 43.8 | [5 empty] | 43.8 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 43.8 | 43.8 |  |  | 43.8 | 0 | 0 | 0 | 1 | 0.62 | 1 | 0.46 | 1 | 100% | 1 | Fe-2019 | 43.34 | Targetted | [10 empty] | 0001781055
3 | Hajin Ananwan | 350 | 0 | 48.8 | 48.8 | [5 empty] | 48.8 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 48.8 | 48.8 |  |  | 48.8 | 0 | 0 | 0 | 3 | 3.83 | 2 | 4.93 | 2 | 67% | 2 | 2019-03-01 | 43.87 | Targetted | [10 empty] | 0005273012
4 | Hamambal Chogal-Haran | 45.7 | 0 | 127.9 | 127.9 | [5 empty] | 127.9 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 127.9 | 127.9 |  |  | 127.9 | 0 | 0 | 0 | 4 | 3.56 | 3 | 3.65 | 3 | 75% | 3 | 2019-03-01 | 124.25 | Targetted | [10 empty] | 0005275194
5 | Haril | 61.29 | 0 | 97.24 | 97.24 | [5 empty] | 97.24 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 97.24 | 97.24 |  |  | 97.24 | 0 | 0 | 0 | 8 | 13.71 | 4 | 1.39 | 4 | 50% | 4 | 2019-03-01 | 95.85 | Targetted | [10 empty] | 0004754678
6 | Lilam Kukroosa | 28.6 | 0 | 130.5 | 130.5 | [5 empty] | 130.5 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 130.5 | 130.5 |  |  | 130.5 | 0 | 0 | 0 | 5 | 36.46 | 5 | 15.16 | 5 | 100% | 1 | 2019-03-01 | 115.34 | Targetted | [10 empty] | 0007274658
7 | Muqami Hindwandpora | 14.9 | 0 | 61.4 | 61.4 | [5 empty] | 61.4 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 61.4 | 61.4 |  |  | 61.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 61.4 | Targetted | [8 empty] | 0004729586
8 | Neelipora Magam | 143.13 | 0 | 79.5 | 79.5 | [5 empty] | 79.5 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 79.5 | 79.5 |  |  | 79.5 | 0 | 0 | 0 | 5 | 22 | 4 | 22.61 | 4 | 80% | 4 | 2019-02-01 | 56.89 | Targetted | [10 empty] | 0004729538
9 | Punzwa | 164.1 | 0 | 116.28 | 116.28 | [5 empty] | 116.28 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 116.28 | 116.28 |  |  | 116.28 | 0 | 1.78 | 1.78 | 1 | 0.67 | 1 | 0.68 | 1 | 100% | 1 | 2019-03-01 | 115.6 | Targetted | [10 empty] | 0004754677
10 | Ramhal | 30 | 0 | 197.44 | 197.44 | [5 empty] | 197.44 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 197.44 | 197.44 |  |  | 197.44 | 0 | 0 | 0 | 6 | 30.5 | 6 | 18.34 | 6 | 100% | 2 | 2019-03-01 | 179.1 | Targetted | [10 empty] | 0005410686
11 | Sheikhpora Ananwan | 199 | 0 | 145.21 | 145.21 | [5 empty] | 145.21 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 145.21 | 145.21 |  |  | 145.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2019-03-01 | 145.21 | Targetted | [10 empty] | 0004729611
12 | Shiltra | 130.68 | 0 | 80.89 | 80.89 | [5 empty] | 80.89 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 80.89 | 80.89 |  |  | 80.89 | 0 | 0 | 0 | 3 | 2.15 | 3 | 3.1 | 3 | 100% | 3 | 2019-03-01 | 77.79 | Targetted | [10 empty] | 0002649700
13 | Takiya Devspora | 133 | 0 | 131.8 | 131.8 | [5 empty] | 131.8 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 131.8 | 131.8 |  |  | 131.8 | 0 | 0 | 0 | 2 | 2.27 | 1 | 0.57 | 1 | 50% | 1 | 2019-01-01 | 131.23 | Targetted | [10 empty] | 0005079573
14 | Vodhpora Khuramabad | 199 | 0 | 45.17 | 45.17 | [5 empty] | 45.17 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 45.17 | 45.17 |  |  | 45.17 | 0 | 0 | 0 | 5 | 8.35 | 5 | 10.96 | 4 | 80% | 4 | 2019-01-01 | 34.21 | Targetted | [10 empty] | 0005079643
15 | Wani Mohalla Budchatri | 145 | 0 | 85.64 | 85.64 | [5 empty] | 85.64 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 85.64 | 85.64 |  |  | 85.64 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0% | 0 | 2019-02-01 | 85.64 | Targetted | [10 empty] | 0002671727
16 | Waskura | 131.5 | 0 | 198.44 | 198.44 | [5 empty] | 198.44 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 198.44 | 198.44 |  |  | 198.44 | 0 | 0 | 0 | 4 | 10.46 | 4 | 14.89 | 4 | 100% | 4 | 2019-03-01 | 183.55 | Targetted | [10 empty] | 0006961420
17 | Aug.Magam Danistan | 99.88 | 0 | 93.85 | 93.85 | [5 empty] | 93.85 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 93.85 | 93.85 |  |  | 93.85 | 0 | 1.07 | 1.07 | 4 | 28.28 | 4 | 28.06 | 2 | 50% | 2 | 2019-02-01 | 65.79 | Targetted | [10 empty] | 0005272240
18 | Vogbal | 152.72 | 0 | 23.98 | 23.98 | [5 empty] | 23.9 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 23.98 | 23.98 |  |  | 23.98 | 0 | 0 | 0 | 2 | 5.22 | 1 | 0 | 0 | 0% | 0 | 2019-03-01 | 23.9 | Targetted | [10 empty] | 0005273282
19 | Construction of 0.60 MGD RSF at Zagsundri | 0 | 0 | 139.32 | 139.32 | [5 empty] | 139.32 | [8 empty] | 0 | 0 | 0 |  |  | 0 | 0 | 139.32 | 139.32 |  |  | 139.32 | 3 | 25 | 28 | 5 | 34.4 | 1 | 0 | 1 | 0% | 0 | 2019-03-01 | 139.32 | Targetted | [10 empty] | 0005079602
20 | Pandithpora Yaroo | 355.77 |  |  | 216.9 | [5 empty] | Total 4: 216.9; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 4.63; CSS 10: 1; CSS 11: 0; CSS 12: 0; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-03-01 | 216.9 | Targetted
21 | Lower Marver | 378.34 |  |  | 223.73 | [5 empty] | Total 4: 223.73; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 59.71; CSS 10: 1; CSS 11: 5.49; CSS 12: 1; CSS 13: 25%; CSS 14: 1; CSS 15: 2019-03-01 | 218.24 | Targetted | [10 empty] | 0004754679
22 | Mughalpora Zamanpora | 207 |  |  | 243.63 | [5 empty] | Total 4: 243.63; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 5.26; CSS 10: 1; CSS 11: 0; CSS 12: 1; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-10-01 |  |  | 243.63 | Targetted | [8 empty] | 0002653345
23 | Khumboora | 516 |  |  | 169.87 | [5 empty] | Total 4: 169.87; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 9; CSS 9: 37.16; CSS 10: 6; CSS 11: 19.02; CSS 12: 6; CSS 13: 66%; CSS 14: 3; CSS 15: 2019-03-01 | 150.85 | Targetted | [10 empty] | 0005017754
24 | Khan Tulwari Checki Langate | 262 |  |  | 74.15 | [5 empty] | Total 4: 74.15; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 20.07; CSS 10: 1; CSS 11: 18.11; CSS 12: 1; CSS 13: 33%; CSS 14: 1; CSS 15: 2019-03-01 | 56.04 | Targetted | [10 empty] | 0002653294
25 | Peer Khan Mohalla | 0 |  |  | 91.5 | [5 empty] | Total 4: 91.5; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 48.63; CSS 10: 6; CSS 11: 14.74; CSS 12: 6; CSS 13: 86%; CSS 14: 6; CSS 15: 2019-02-01 | 76.76 | Targetted | [10 empty] | 0002653286
26 | Baripora Chogal | 0 |  |  | 197.21 | [5 empty] | Total 4: 197.21; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 5; CSS 9: 26.25; CSS 10: 5; CSS 11: 16.05; CSS 12: 5; CSS 13: 100%; CSS 14: 3; CSS 15: 2019-03-01 | 181.16 | Targetted
27 | Kachloo Khaipora | 0 |  |  | 984 | [5 empty] | Total 4: 984; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 3; CSS 9: 198.46; CSS 10: 1; CSS 11: 41; CSS 12: 1; CSS 13: 33%; CSS 14: 0; CSS 15: 2019-03-01 | 943 | Targetted
28 | Langate Town | 0 |  |  | 720.64 | [5 empty] | Total 4: 720.64; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 44.7; CSS 10: 0; CSS 11: 0; CSS 12: 2; CSS 13: 0%; CSS 15: 2019-03-01 | 720.64 | Targetted
29 | Rajpora Khaipora | 275 |  |  | 214 | [5 empty] | Total 4: 214; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 2; CSS 9: 5.68; CSS 10: 1; CSS 11: 0.63; CSS 12: 1; CSS 13: 50%; CSS 14: 1; CSS 15: 2019-02-01 | 213.37 | Targetted | [10 empty] | 0002653356
30 | Kishtiwari Nowgam | 310.15 |  |  | 105.75 | [5 empty] | Total 4: 105.75; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 33.72; CSS 10: 1; CSS 11: 0.36; CSS 12: 1; CSS 13: 25%; CSS 14: 1; CSS 15: 2019-03-01 | 105.39 | Targetted | [10 empty] | 0002671766
31 | Marsari Pachkote | 574 |  |  | 208.9 | [5 empty] | Total 4: 208.9; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 4; CSS 9: 25.95; CSS 10: 4; CSS 11: 20.02; CSS 12: 2; CSS 13: 50%; CSS 14: 2; CSS 15: 2019-03-01 | 188.88 | Targetted | [10 empty] | 0002653302
32 | Sonmullaa Tulwari | 202.1 |  |  | 163 | [5 empty] | Total 4: 163; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 1; CSS 9: 11.8; CSS 10: 0; CSS 11: 0; CSS 12: 1; CSS 13: 0%; CSS 14: 0; CSS 15: 2019-03-01 | 163 | Targetted | [10 empty] | 0001767975
33 | Aug.Pohru peth palpora | 100 |  |  | 790 | [5 empty] | Total 4: 790.25; MSS 5: 0; CSS 6: 0; CSS 7: 0; CSS 8: 7; CSS 9: 42.45; CSS 10: 2; CSS 11: 7.37; CSS 12: 2; CSS 13: 30%; CSS 14: 2; CSS 15: 2019-03-01 | 782.88 | Targetted | [10 empty] | 0005087062
33 | Total | 5291.36 | 0 | 1899.01 | 6302.29 | 0 | 0 |  |  |  | 6302.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1899.01 | 1899.01 | 0 | 0 | 1899.01 | 3 | 100.05 | 103.05 | 118 | 789.77 | 79 | 275.81 | 75 |  | 55 |  | 5721.62 | 31 | 305.03 | 2
60 | Total District Kupwara | 7568.44 | 0 | 5187.25 | 15173.52 | 0 | 101.54 |  |  |  | 11294.5 | [8 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 3 | 100.05 | 103.05 | 185 | 1223.34 | 111 | 500.73 | 90 |  | 55 | 0 | 7448.86 | 39 | 3344.91 | 21 | [11 empty] | 10793.77
1 | Provision for Constrution of Hand Pumps |  | 0 | 2200 | 2200 | [5 empty] | Total 4: 2200; Total 9: State Sector Refular Capex Budget; Total 17: 0; Total 18: 0; Total 19: 0; Total 22: 0; Total 23: 0; Total 24: 2200; Total 25: 2200; Total 28: 2200; CSS 8: 400; CSS 14: 0 | 0 |  | 2200 | 1
314 | Grand Total :- | 38850.11 | 0 | 32243.19 | 81807.98 | 0 | 101.54 |  |  |  | 56201.21 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 188.12 | 1291.23 | 1479.35 | 1754 | 9074.849 | 843 | 4700.0257 | 449 | 0 | 78 |  | 9940.7043 | 116 | 41560.48 | 197
Chief Enginer
Kashmir PHE Department
Srinagar